## Project_FactSheet
Project Name: | Addressing Life Saving Access to Solar Water Provision in Madani Locality Al Gezira
Donor: | UN_Central Emergency Response Fund (CERF)
Total budget: | 1200000.85
Start date: | 2025-06-02
End date: | 2026-06-01
Duration: | 12 months
Target locations: | Madani Locality, Al Gezira
Implementing Partners: | NA
Last update to tracker:

## CERF_Tracker
Outcome | Activity | Output | Indicators | Target | Actual | Actual_Jan | Comment | EoP
Improved and sustained access to safe water for conflict-affected communities in Gezira, contributing to reduced health risks, enhanced community resilience, and short-term livelihood opportunities for displaced and vulnerable populations. | Activity 1.1.1: Community consultation and strengthening of CMC | 1.1. Restored and Solarized Water Infrastructure for Equitable Access 30 non-functional water yards rehabilitated and equipped with solar power systems, ensuring reliable and sustainable access to clean water for at least 180,000 people from host communities and displaced populations in Gezira. | Indicator 1.1.1 (Custom): Number of persons benefitted from 36 water yards rehabilitation and solarization, providing access to clean water for targeted population. | 180000 |  | 206720 | Completed | 37 + 7 (Additional) = 44 sites
Activity 1.1.2: CMC and UNDP Area-Office Rapid planning and implementation arrangements for rehabilitation of water yards
Activity 1.1.3. Procurement of Goods and Services through LTA arrangements
Activity 1.1.4: Rehabilitation of Water Yards and awareness creation
| Activity 1.2.1: Joint Meeting and consultation with humanitarian agencies and subcluster level for targeting community and beneficiaries | 1.2 Cash-for-Work Livelihoods Created for 1,000 displaced and vulnerable individuals, including women and youth, engaged in cash-for-work initiatives over two months to support water infrastructure repairs, generating short-term income while contributing to community resilience and essential service delivery. | Indicator 1.2.1 (Custom): Number of displaced and vulnerable individuals, including women and youth, engaged in cash-forwork for at least two months to support water infrastructure repairs and generate short-term income | 1000 |  | 1100 | Completed | 1155 (gender breakdown - TBC) | Alradma- area selected based on advice of WASH cluster, area suffered from disease outbreak, CfW scheme involved cleaning campaign. MoH was also present in that meeting explaining waste crisis, lack of waste disposal.
| Activity 1.2.2: Selection, registration and orientation of beneficiaries on CfW modality and SES including GRM |  | Indicator 1.2.2 (Standard): (CASH) Number of people receiving Conditional cash transfers | 1000 |  | 1100 |  | 1155 (gender breakdown - TBC) | 1155
| Activity 1.2.3: Implementation of CfW activity for water yards rehabilitation. |  | Indicator 1.2.3 (Standard): (CASH) Total value of Conditional cash transfers distributed in USD | 150000 |  |  |  | TBC from financial report | Each person received ~ $10-~11/day, engaged for 10 days. Depends on UNDP rate (first rate 2240 and last rate was 3800)
Activity 1.2.4: Cash distribution and Post Distribution Monitoring
183600
|  |  |  | 120120 | 101918.49 | 222038.49
38438.49
29880
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sanaa Saeed / @Mustafa Hassan please update this column as of end of Jan Reply: I didn't understand, could you explain further?

## CERF_WaterSites
SOW | Location of the water station | Locality | Site Coordinates | Production Discharge Rate (m³/h) (Update data based on water station productivity) | Expected Drawdown (m) | Pump Size (KW) | Pump Selection Type & Model | Total panels in a 580W panel-scale station | Number of hours it operates on solar system for borehole | Solar water production Rate (m3/day) for Station | Water productivity per liter/day | Total of direct beneficiaries of water stations (person) | Total of women beneficiaries of water stations (person)65% | Total of men beneficiaries of water stations (person)35% | Providing livelihoods through cash for work for 60% of male beneficiaries (SOW for CASH foe Work ) water, Sanitation and Hygiene)+Water station rehabilitation | Handed_Over | Handover_Date
Supply delivery and installation of solar system for 18KW Pump and steel fence | in purification station محطة التنقية | Greater Medani Locality | N 14.40785 E 33.53151 | 57 | 0.7 | 18 KW | DAB-SS6C 04-3inch | 46 | 8 | 456 | 456000 | 9120 | 3648 | 5472 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 18 KW Pump and steel fence | Gazira ALMAKA محطةالمكي | Greater Medani Locality | N 14.415751 E 33.557028 | 55 | 0.9 | 18 KW | DAB-SS6C 04-3inch | 46 | 8 | 440 | 440000 | 8800 | 5720 | 3080 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 15 KW Pump and steel fence | Southern Textiles نسيج الجنوبية | Greater Medani Locality | N 14.36291 E 33.52989 | 46 | 0.74 | 15KW | DAB-SS6C 04-3inch | 40 | 8 | 368 | 368000 | 7360 | 2944 | 4416 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW pump and steel fence | حي دردق ناصر Dardak Nasser neighborhood | Greater Medani Locality | N 14.414554 E 33.549667 | 28 | 0.67 | 7.5 KW | DAB-SS6C 04-3inch | 30 | 8 | 224 | 224000 | 4480 | 1792 | 2688 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system 7.5 KW pump and steel fence | Elrian الريان | Greater Medani Locality | N 14.44675 E 33.56203 | 26 | 0.92 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 208 | 208000 | 4160 | 1664 | 2496 | 70 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system 11Kwpump and steel fence | Northern Textile District منطقة النسيج الشمالية | Greater Medani Locality | N 14.36575 E 33.52997 | 43 | 1.2 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 344 | 344000 | 6880 | 2752 | 4128 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system 11 kw pump and steel fence | Executive Office Water Station | Greater Medani Locality | N 14.36724 E 33.50357 | 35 | 2.3 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 280 | 280000 | 5600 | 2240 | 3360 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system 7.5 Kw and steel fence | in Al-Waha neighborhood حي الواحة | Greater Medani Locality | N 14.39855 E 33.53418 | 29 | 0.88 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 232 | 232000 | 4640 | 1856 | 2784 | 0 | 2026-01-12 | 2026-01-12 |  | 0
Supply delivery and installation of system for 11 KW Pump and steel fence | Barakat بركات | Greater Medani Locality | N 14.32092 E 33.54726 | 41 | 0.67 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 328 | 328000 | 6560 | 2624 | 3936 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of system for 11 KW Pump and steel fence | Mobi Elthwora Al Qadima موبي الثورة القديمة | Greater Medani Locality | N 14.3695 E 33.4813 | 37 | 3.6 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 296 | 296000 | 5920 | 2368 | 3552 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 11 KW Pump and steel fence | Mobi Elthwora Area Elthwora موبي الثورة حي الثورة | Greater Medani Locality | N 14.37153 E 33.47652 | 40 | 1.2 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 320 | 320000 | 6400 | 2560 | 3840 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW Pump and steel fence | Mobi Elthwora موبي الثورة مربع 6 | Greater Medani Locality | N 14.37572 E 33.47628 | 32 | 0.78 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 256 | 256000 | 5120 | 2048 | 3072 | 0 | 2026-01-12 | 2026-01-12
Rehabilitation for the borehole Supply delivery and installation of solar system for 7.5 KWsubmersible Pump and steel fence | Mobi Elthwora Al-Salam Area موبي الثورة حي السلام | Greater Medani Locality | N 14.37528 E 33.48333 | 34 | 0.9 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 272 | 272000 | 5440 | 2176 | 3264 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Zamalek neighborhood حي الزمالك | Greater Medani Locality | N 14.40598 E 33.50175 | 35 | 1.1 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 280 | 280000 | 5600 | 2240 | 3360 | 39 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Dar Um Bilalدار ام بلال- | Greater Medani Locality | N 14.3318 E 33.54721 | 32 | 0.67 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 256 | 256000 | 5120 | 2048 | 3072 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Marinjan مارنجان الفسحة | Greater Medani Locality | N 14.34487 E 33.53561 | 38 | 2.3 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 304 | 304000 | 6080 | 2432 | 3648 | 37 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Riyadh block 3 الرياض مربع 3 | Greater Medani Locality | N 14.44291 E 33.53619 | 35 | 4.5 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 280 | 280000 | 5600 | 2240 | 3360 | 52 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Riyadh block 4 الرياض مربع4 | Greater Medani Locality | N 14.43704 E 33.52553 | 29 | 0.9 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 232 | 232000 | 4640 | 1856 | 2784 | 60 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Almzad المزاد | Greater Medani Locality | N 14.38418 E 33.5089 | 31 | 3.1 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 248 | 248000 | 4960 | 1984 | 2976 | 37 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | New Rayyan الريان جديدة | Greater Medani Locality | N 14.44675 E 33.56203 | 38 | 4 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 304 | 304000 | 6080 | 2432 | 3648 | 67 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Al dnagla الدناقلة | Greater Medani Locality | N 14.34325 E 33.60152 | 36 | 1.9 | 7.5 KW | DAB-SS6C 04-3inch | 3 | 8 | 288 | 288000 | 5760 | 2304 | 3456 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Al Nasser الناظر | Greater Medani Locality | N 14.32498 E 33.61667 | 39 | 2.1 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 312 | 312000 | 6240 | 2496 | 3744 | 63 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | ALTaif block 299 NEWالطائف 299الجديدة | Greater Medani Locality | N 14.37451 E 33.5243 | 33 | 0.98 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 264 | 264000 | 5280 | 2112 | 3168 | 47 | 2026-01-12 | 2026-01-12
Supply delivery and installation of solar system for 7.5 KW submersible Pump and steel fence | Abu Haraz village ابوحراز | Greater Medani Locality | N 14.48666 E 33.51243 | 31 | 1.4 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 248 | 248000 | 4960 | 1984 | 2976 | 45 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 11 KW Pumpand steel fence | Bant village قرية بانت | Umm Al-Qura | N 14.44339 E 33.93492 | 42 | 0.6 | 11 KW | DAB-SS6C 04-3inch | 30 | 8 | 336 | 336000 | 6720 | 2688 | 4032 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and Supply delivery and installation of Pump7.5 kw and steel fence and supply and installation of surface pumps7.5 KW | Village 38 القرية 38 | Umm Al-Qura | N 14.40456 E 33.84354 | 29 | 5.4 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 232 | 232000 | 4640 | 1856 | 2784 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 22 KW Pumpand steel fence | Ain Al-Lawaiqa A محطة عين اللويقة ا | Umm Al-Qura | N 14.1947 E 33.93533 | 51 | 1.7 | 22 KW | DAB-SS6C 04-3inch | 58 | 8 | 408 | 408000 | 8160 | 3264 | 4896 | 0 | 2026-01-12 | 2026-01-12 | 0
Supply delivery and installation of Solar system for 4 KW Pumpand steel fence | Ain Al-Lawaiqa B محطة عين اللويقة ب | Umm Al-Qura | N 14.1716 E 33.93687 | 18 | 3.2 | 4 KW | DAB-SS6C 04-3inch | 12 | 8 | 144 | 144000 | 2880 | 1152 | 1728 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | Umm Al-Qura Camp المخيم ام القري | Umm Al-Qura | N 14.39316 E 33.78432 | 27 | 3.4 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 216 | 216000 | 4320 | 1728 | 2592 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | Transmission Line Camp المخيم الخط الناقل | Umm Al-Qura | N 14.39316 E 33.78433 | 28 | 0.9 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 224 | 224000 | 4480 | 1792 | 2688 | 48 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | ALwahda shraq Almusrf الوحدة شرق المصرف | Umm Al-Qura | N 14.45601 E 33.9272 | 32 | 0.73 | 40 KW | DAB-SS6C 04-3inch | 104 | 8 | 256 | 256000 | 5120 | 2048 | 3072 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 45 KW Pump in Wad Al-Abyad Collection Basin+ Supply and installation of surface pump 45KW + Supply and installation of surface pumpsand steel fence 22kW | Wad Al-Abyad Village Basin Collection حوض تجميع قرية ود الابيض | Umm Al-Qura | N 14.39317 E 33.78425 | 85 | 1.3 | 45 KW | DAB-SS6C 04-3inch | 116 | 8 | 680 | 680000 | 13600 | 5440 | 8160 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | Ruwina Al-Arkiyyin Village قرية روينا العركيبن | Umm Al-Qura | N 14.91576 E 33.41237 | 32 | 2.88 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 256 | 256000 | 5120 | 2048 | 3072 | 0 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | Tambool Sq 9 تمبول مربع | Tambool | N 14.91039 E 33.4152 | 37 | 3.5 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 296 | 296000 | 5920 | 2368 | 3552 | 47 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pumpand steel fence | Tambool Alaishab العيشاب | Tambool | N 14.482845 E 33.609722 | 35 | 0.9 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 280 | 280000 | 5600 | 2240 | 3360 | 47 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | AL Heglig الهجليج | Tambool | N 14.88671 E 33.34415 | 29 | 0.89 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 232 | 232000 | 4640 | 1856 | 2784 | 49 | 2026-01-12 | 2026-01-12
Supply delivery and installation of Solar system for 7.5 KW Pump and steel fence | حي اركويت Arkawit neighborhood | Greater Medani Locality | N 14.389269 E 33.544283 | 24 | 1.67 | 7.5 KW | DAB-SS6C 04-3inch | 19 | 8 | 192 | 192000 | 3840 | 1536 | 2304 | 48 | 2026-01-12 | 2026-01-12
| Alradma الرضمة | Southren Al Gazira | [12 empty] | 107
Supply delivery and installation of 7 solar system for exesting pumps | Almoneeraالمنيرة | Madani Alkubra locality | N 14.739078 E 33.532993 | 40 | 3 | 7.5 KW | submersable pump 3 inch | 15 | 8 | 320 | 320000 | 6400 | 4160 | 2240 | 0 | YES | 2026-07-02
Supply delivery and installation of 7 solar system for exesting pumps | Sukar lbangarسكر البنجر | Madani Alkubra locality | N 14.371092 E 33.533121 | 35 | 3 | 7.5 KW | submersable pump 3 inch | 15 | 8 | 280 | 280000 | 5600 | 3640 | 1960 | 0 | YES | 2026-07-02
Supply delivery and installation of 7 solar system for exesting pumps | Petrolume head officeإدارة البترول | Madani Alkubra locality | N 14.399086 E 33.501232 | 45 | 3.7 | 7.5 KW | Algo -india- submersable pump 3 inch | 15 | 8 | 360 | 360000 | 7200 | 4680 | 2520 | 0 | YES | 2026-07-02
Supply delivery and installation of 7 solar system for exesting pumps | Banat بانت | Madani Alkubra locality | N 14.410751 E 33.493010 | 45 | 3 | 7.5 KW | submersable pump 3 inch | 15 | 8 | 360 | 360000 | 7200 | 4680 | 2520 | 0 | YES | 2026-07-02
Supply delivery and installation of 7 solar system for exesting pumps | Alshabarga الشبارقة | Madani Alkubra locality | N 14.250590 E 33.493010 | 45 | 4 | 7.5 KW | submersable pump 3 inch | 15 | 8 | 320 | 320000 | 6400 | 4160 | 2240 | 0 | YES | 2026-07-02
Supply delivery and installation of 7 solar system for exesting pumps | Aleishab العيشاب | Um Algura locality | N 14.401270 E 33.697473 | 25 | 4 | 7.5 KW | submersable pump 2 inch | 15 | 8 | 200 | 200000 | 4000 | 2600 | 1400 | 0 | YES | 2026-07-02
Supply delivery and installation of 7 solar system for exesting pumps | Ain allowega-C- عين اللويقة | Um Algura locality | N 14.153773 E 33.924567 | 25 | 9 | 7.5 KW | submersable pump 2 inch | 15 | 8 | 200 | 200000 | 4000 | 2600 | 1400 | 0 | YES | 2026-07-02
[8 empty] | 105 |  | 2040 | 2040000 | 63040 | 115056 | 141584
[13 empty] | 22016 | 33024
256640
144
Note on Q1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Mustafa Hassan Please update this column with sites handed over recently Reply: I didn't understand the handover date from the company or to the water authority. Reply: I didn't understand the handover date from the company or to the water authority. Reply: @Mustafa Hassan to the water authority so these would be the date of the opening ceremony for example
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No water station was implemented by UNDP ; only activity was carried out (CFW).

## Beneficiaries
| Target | % | Actual |  | Women | Women (>18) | Girls | Men | Men(>18) | Boys
IDP | 108000 | 60% | 153984 |  | 78532 | 47119 | 31413 | 75452 | 45264 | 30188 | CfW beneficiaries AlJazeera State
Refugees | 9000 | 5% | 12832 |  | 6544 | 3926 | 2618 | 6288 | 3773 | 2515 | Group | Female | Status |  | Male | Status
Returnees | 9000 | 5% | 12832 |  | 6544 | 3926 | 2618 | 6288 | 3773 | 2515 |  |  | HC | IDP |  | HC | IDP
HC | 54000 | 30% | 76992 |  | 39266 | 23560 | 15706 | 37726 | 22636 | 15090 | 1 | 37 | 30 | 7 | 203 | 162 | 41
[11 empty] | 2 | 47 | 38 | 9 | 203 | 162 | 41
[11 empty] | 3 | 62 | 50 | 12 | 173 | 138 | 35
[11 empty] | 4 | 76 | 61 | 15 | 177 | 142 | 35
[7 empty] | Protection Target | 135000 |  |  | 5 | 92 | 74 | 18 | 85 | 68 | 17
[7 empty] | Protection Actual | 130885 |  |  |  | 314 | 251 | 63 | 841 | 673 | 168
| Final | 256640 | [15 empty] | 1155
| Female | 130886.4 | 130885 | [14 empty] | 27.19%
| Girls | 81148.7 | 81149 |  | 49736 |  | Women |  |  |  | Youth | 62% | Girls & Boys
| Male | 125753.6 | 125755 | [7 empty] | Children | 40%
| Boys | 77968.1 | 77967 |  | 47788 |  | Men |  |  |  | Female | 51% | Women & Girls
[11 empty] | Male | 49% | Men & Boys
| Women | Girls | Men | Boys
IDP | 78531.84 | 31412.736 | 75452.16 | 30180.864
Refugees | 6544.32 | 2617.728 | 6287.68 | 2515.072
Returnees | 6544.32 | 2617.728 | 6287.68 | 2515.072
HC | 39265.92 | 15706.368 | 37726.08 | 15090.432

## Consolidated Annual Operational
Estimated Annual Cost
Exchange Rate 3500, Cost of Gallon 21000
Pump Type (kW) | No. Solar Pumps | Fuel Cost per Gallon (USD) | Fuel Consumption per Day (Gallons) | Operating Days per Year | Annual Fuel Cost (USD)
7.5 kw | 22 | 6 | 2 | 365 | 96360
11 kw | 8 | 6 | 5 | 365 | 87600
18 kw | 2 | 6 | 7 | 365 | 30660
15 kw | 1 | 6 | 6 | 365 | 13140
45 kw | 1 | 6 | 9 | 365 | 19710
40 kw | 1 | 6 | 9.5 | 365 | 20805
22 kw | 1 | 6 | 8 | 365 | 17520
4 kw | 1 | 6 | 1 | 365 | 2190
Total | 37
Total of Fuel cost per year for 37 solar System |  |  |  |  | 287985
Consolidated Annual Operational Cost (Diesel System)
Cost Component | Estimated Annual Cost (USD)
Fuel | 287985
Maintenance | 255000 |  |  | Calculated Greenhouse Gas Emission Reduction
Spare Parts | 185000
Lubricants | 98000 |  | Diesel Saved⛽ | CO2 Emission Factor (kg CO₂/gal) | Total CO2 Reduction (tCO₂)
Transport & Handling | 175000 |  | 47,997.5 Gallons | 10.19 kg CO2/gal | 489.094 Tons
Cost savings achieved by the state government in the year | 1000985

## Weekly_Updates
Week Duration | Update_Water | Update_CfW
16th Nov to 20th Nov | Provision of 37 Water Yards – Contractor Name: • Madani Alkubra: Solar system installation has reached 80% completion across 20 water yards. • Tamboul: Rehabilitation works are 90% completed at 3 sites. • Um Algora: Rehabilitation works have reached 40% completion at 4 sites. | Cash-for-Work (CfW): • Third phase of CfW activities is 90% completed in five locations. • PCA for the fourth phase of CfW activities, approved and submitted to the finance for processing.
23rd Nov to 27th Nov | Provision of 37 Water Yards : • Completed 100% of civil works and solar system installations for 23 sites in Madani Al-Kubra. • Achieved 70% of solar system installations for 2 sites in Madani. • Completed solar system installations for 100% of rehabilitation works at 3 sites in Tambool. • Completed 100% of solar system installations for at 4 sites in Umalgora. • Achieved 50% solar system installations and rehabilitation works at 5 sites in Umalgora. • Joined a site visit in Madani to completed water yards with HAC, MoF, and the Water Corporation to prepare for the handover event. | Cash-for-Work (CfW): • phase three of CfW activities is 100% completed, liquidation submitted for reviewing. • CfW activities - phase four, initiated for five location. • Conducted five meetings with Community Management Committees (CMC) to ensure active community participation in the Cash-for-Work (CFW) intervention.
30th Nov to 4th Dec | 1. Provision of 37 Water Yards :  Completed 100% of civil works and solar system installations for 24 sites in Madani Al-Kubra.  Achieved 80% of solar system installations for 1 sites in Madani.  Completed 100% of solar system installations for at 6 sites in Umalgora.  Achieved 70% solar system installations and rehabilitation works at 5 sites in Umalgora. | 2.Cash-for-Work (CfW): • phase four reached 40% completion in five location.
7th Dec to 11th Dec | 1. Provision of 37 Water Yards :  Panels have been installed, fencing erected, and 45 kW and 22 kW pumps installed at Wad Al Abyad site  Achieved 80% of solar system installations for 1 sites in Madani.  Panels and inverters have been installed at 5 sites in Umm Al Qura.  Achieved 80% solar system installations and rehabilitation works at 5 sites in Umalgora. | 2.Cash-for-Work (CfW): • phase four reached 80% completion in five location.
14th Dec to 18th Dec | . Provision of solar system and rehabilitation of 37 water yards in Gezira state: (CERF Funded project) - Completion 100% of civil works and 99% of Solar system installation for 25 sites Madani Al-Kubra. Only 4signboards remain; they will be completed by Saturday. - Completion 100% of rehabilitation works for 3 sites in Tambool. - Completion 100% of materials delivery and Completion 100 %of rehabilitation works for 9 sites in Umalgora. | 2.Cash-for-Work (CfW): • Completion 100% of Cash for Work phase four in five location. • Liquidation expected to submitted on Sunday 21Dec.2025.
21st Dec to 25th Dec | • Solar system installation, 100% completed at 25 sites in Madani Al-Kubra. • Solar panels and inverters have been installed at 9 sites in Umm Al Qura. • At Wad Al Abyad, solar panels, installed, fencing completed, ( 45 kW )and( 22 kW) pumps installed at the designated sites. • At Village 38 ( 7.5 kW ) pump has been installed. | 2.Cash-for-Work (CfW): • Liquidation for Cash for Work phase four completed. • Arrangement for last group targeted 57 individual initiated.
28th Dec to 31st Dec | • Training was conducted for technicians and 37 water committees in Madani locality, Um Al Gura, and Tambool on the operation and maintenance of solar systems. | 2. Cash-for-Work (CfW): • The final Cash-for-Work intervention targeting 57 individuals was initiated in the Alrayan area.
4th Jan to 8th Jan | Provision of Solar Systems and Rehabilitation of 37 Water Yards in Gezira State (CERF-Funded Project): • Coordination and arrangements for the handover of 37 water yards have been completed. | 2- Cash-for-Work (CfW): • The final Cash-for-Work intervention has reached 95% completion.
11th Jan to 15th Jan | CERF-Funded Project: The handover of 37 water yards was successfully completed under the CERF-funded project. | Cash for work intervention was successsfully completed benefited 1100 individual
18th Jan to 22nd Jan
25th Jan to 29th Jan
15th Feb to 19th Feb
22nd Feb to 26th Feb |  | PCA for last group of CFW approvd and submitted to finance but not recieved money yet
1st Mar to 5th Mar
8th Mar to 12th Mar
15th Mar to 19th Mar
22nd Mar to 26th Mar
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sanaa Saeed / @Mustafa Hassan kindly provide a training report documenting this using the shared template

## Water_Locations
State | IP | Locality | Town/Community
Al Jazeera | UNDP_RR | Greater Medani Locality | Madani town Purification station
Al Jazeera | UNDP_RR | Greater Medani Locality | Jazeera ALMAKI
Al Jazeera | UNDP_RR | Greater Medani Locality | Southern Textiles
Al Jazeera | UNDP_RR | Greater Medani Locality | Dardak Nasser neighborhood
Al Jazeera | UNDP_RR | Greater Medani Locality | El-Rayan
Al Jazeera | UNDP_RR | Greater Medani Locality | Northern Textile District
Al Jazeera | UNDP_RR | Greater Medani Locality | Executive Office Water Station
Al Jazeera | UNDP_RR | Greater Medani Locality | Al-Waha neighborhood
Al Jazeera | UNDP_RR | Greater Medani Locality | Barakat
Al Jazeera | UNDP_RR | Greater Medani Locality | Mobi Elthwora Al Qadima
Al Jazeera | UNDP_RR | Greater Medani Locality | Mobi Elthwora Area Elthwora
Al Jazeera | UNDP_RR | Greater Medani Locality | Mobi Elthwora
Al Jazeera | UNDP_RR | Greater Medani Locality | Mobi Elthwora Al-Salam Area
Al Jazeera | UNDP_RR | Greater Medani Locality | Zamalek neighborhood
Al Jazeera | UNDP_RR | Greater Medani Locality | Dar Um Bilal
Al Jazeera | UNDP_RR | Greater Medani Locality | Marinjan
Al Jazeera | UNDP_RR | Greater Medani Locality | Riyadh block 3
Al Jazeera | UNDP_RR | Greater Medani Locality | Riyadh block 4
Al Jazeera | UNDP_RR | Greater Medani Locality | Almzad
Al Jazeera | UNDP_RR | Greater Medani Locality | New Rayan
Al Jazeera | UNDP_RR | Greater Medani Locality | Al Danagla
Al Jazeera | UNDP_RR | Greater Medani Locality | Al Nasser
Al Jazeera | UNDP_RR | Greater Medani Locality | New Al-Taif block 299
Al Jazeera | UNDP_RR | Greater Medani Locality | Abu Haraz village
Al Jazeera | UNDP_RR | Umm Al-Qura | Bant village
Al Jazeera | UNDP_RR | Umm Al-Qura | Village 38
Al Jazeera | UNDP_RR | Umm Al-Qura | Ain Al-Lawaiqa A
Al Jazeera | UNDP_RR | Umm Al-Qura | Ain Al-Lawaiqa B
Al Jazeera | UNDP_RR | Umm Al-Qura | Umm Al-Qura Camp
Al Jazeera | UNDP_RR | Umm Al-Qura | Transmission Line Camp
Al Jazeera | UNDP_RR | Umm Al-Qura | Al-Wahda shraq Almusrf
Al Jazeera | UNDP_RR | Umm Al-Qura | Wad Al-Abyad Village Basin Collection
Al Jazeera | UNDP_RR | Umm Al-Qura | Ruwina Al-Arkiyyin Village
Al Jazeera | UNDP_RR | Tambool | Tambool Sq 9
Al Jazeera | UNDP_RR | Tambool | Tambool Alaishab
Al Jazeera | UNDP_RR | Tambool | Al Heglig
Al Jazeera | UNDP_RR | Greater Medani Locality | Arkawit neighborhood