## Project_FactSheet
Project Name: | Enhancing Access To Water Infrastructure For IDPs Refugees And Host Communities Project in the Republic of Sudan
Award No: | 1382316–Kuwait (447)
Donor: | Kuwait Fund for Arab Economic Development (KFAED)
Total budget: | 2000000
Start date: | 2025-04-24
End date: | 2026-04-01
Project Duration: | 12 months
Target locations: | River Nile, Gedaref, Sennar, Al Gazeera
Implementing Partners: | -
Last update to tracker: | 2026-02-23

## Kuwait_Tracker
Outcome | Output | Activity | PIMS_ToI | Target | Estimated Total ($) | Actual (12.11) | Actual (10.02) |  | Comment
Improved infrastructure in Sudan for accessing clean water with reduced risk of waterborne and water related diseases | Output 1: Access of Vulnerable population to clean and safe water improved which meets Sphere and WHO standards in terms of quantity and quality | Activity 1.1 Establish and solarize 8 new water yards and extension of distribution points and installation of solar system |  | 8 | 760000 | 655837.2 |  | 8 | 8 procured as follow: 3 in Gezira, 2 in Sennar, 2 River Nile, 1 Gadarif; The work progress reached 100%.
|  | Activity 1.2 Rehabilitate, upgrade, and solarize 16 existing non-functional water yards and distribution points |  | 16 | 720000 | 596029 | 10 | 16 | 16 procured as follow: 5 in Gezira, 5 in Sennar, 4 River Nile, 2 Gadarif; The work progress reached100%.
| Output 2: Capacity of Communities and local authorities to manage and maintain water infrastructure strengthened | Activity 2.1 Capacity building for local authorities on sustainability and cost recovery system |  | 24 | 120000 | 32896 |  | 24 | Establish 24 Water User Associations (WUAs), each including 10 voluntary members of the community with a Chairperson, Secretary and a Treasurer | Get database of all WUA members in different states due Sunday (19/07)
|  | Activity 2.2 Train 48 Community Water and Solar Technicians (CWSTs) and equip them with toolkits |  | 48 | 120000 | 28160 |  |  | Preparation for conducting the training is made.PCA are prepared and waiting for approval.
[5 empty] | 1720000 | 1312922.2

## Kuwait_RN_WaterSites
Contractor | TRADE HOOK & Hewa for Water Drilling | Rehabilitation of Water Yards- Kuwait Project - RNS
| TOTAL TASKS | 18 |  | Duration | 90 |  | Overall Progress
| Completed | 4 |  | Project Start | 2025-09-17
| In progress | 5 |  | Project End | 2025-12-16 |  | 22%
| Column1 | Responsible | Start Date | End Date | Progress | Status | Duration | Completed | Pending
| Site Handover for first 4 lots |  | 2025-10-02 | 2025-10-09 | 100% | Completed | 7
| Team mobilization |  | 2025-10-09 | 2025-10-16 | 100% | Completed | 7
LOT 1 Hassania Water Yard
LOT 1 | Civil Work |  | 2025-10-16 | 2025-10-23 | 100% | Completed | 7
LOT 1 | PV Panels &Structures |  | 2025-10-16 | 2025-10-19 | 100% | Completed | 3
LOT 1 | Electrical |  | 2025-10-16 | 2025-10-18 | 100% | In progress | 2
LOT 1 | Testing & Commissioing & Handover |  | 2025-10-16 | 2025-10-20 | 100% | In progress | 4
LOT 2 Elaababda Water Yard
LOT 2 | Civil Work |  | 2025-10-20 | 2025-10-27 | 100% | In progress | 7
LOT 2 | PV Panels &Structures |  | 2025-10-27 | 2025-10-30 | 100% | Not Started | 3
LOT 2 | Electrical |  | 2025-10-30 | 2025-11-01 | 100% | Not Started | 2
LOT 2 | Testing & Commissioing & Handover |  | 2025-11-01 | 2025-11-05 | 100% | Not Started | 4
LOT 3 Gabati Water Yard
LOT 3 | Civil Work |  | 2025-11-05 | 2025-11-12 | 100% | In progress | 7
LOT 3 | PV Panels &Structures |  | 2025-11-12 | 2025-11-15 | 100% | Not Started | 3
LOT 3 | Electrical |  | 2025-11-15 | 2025-11-17 | 100% | Not Started | 2
LOT 3 | Testing & Commissioing & Handover |  | 2025-11-17 | 2025-11-21 | 100% | Not Started | 4
LOT 4 Ashwal Water Yard
LOT 4 | Civil Work |  | 2025-11-21 | 2025-11-28 | 100% | In progress | 7
LOT 4 | PV Panels &Structures |  | 2025-11-28 | 2025-12-01 | 100% | Not Started | 3
LOT 4 | Electrical |  | 2025-12-01 | 2025-12-03 | 100% | Not Started | 2
LOT 4 | Testing & Commissioing & Handover |  | 2025-12-03 | 2025-12-07 | 100% | Not Started | 4
Contractor | Abo Sora | Rehabilitation of Water Yards- Kuwait Project - Gazira State
| TOTAL TASKS | 18 |  | Duration | 90 |  | Overall Progress
| Completed | 4 |  | Project Start | 2025-09-17
| In progress | 5 |  | Project End | 2025-12-16 |  | 80%
78%
| Column1 | Responsible | Start Date | End Date | Progress | Status | Duration (days) | Completed | Pending
| Rehabilitaion Existing Water Yards |  | 2025-10-02 | 2025-10-09 | 80% | Completed | 41
| Construction of New Water Yard/projects |  | 2025-10-09 | 2025-10-16 | 80% | Completed | 3

## Weekly_Updates
Week Duration | Progress
30th Nov to 4th Dec | Contractor: Tihraga Engineering for Building Co. (2 sites) • Rehabilitation works at the two Dalse sites have reached 85% completion. • coordination meetings with the Ministry of Production and Social Affairs.
7th Dec to 11th Dec | Kuwait Fund Procurement Projects - Gedaref Contractor: Tihraga Engineering (2 sites) • Rehabilitation works at the Dalse sites have reached 85%. Kuwait Project (Trade Hook Co.) - River Nile • Hassania Water Yard: Completion of civil works 100%. • Al Matama Hospital & Alababda Water Yard: Completion of civil works 100%.. • Village 5 Water Yard: Completion of civil works 20%. Kuwait-Funded Project – Provision of 4 Solar Systems (Sinnar State) * Completion 80 % of the solar system on 4 water yards
14th Dec to 18th Dec | Kuwait Fund Procurement Projects - Gedaref Contractor: Tihraga Engineering (2 sites) • Rehabilitation works at the Dalsa sites have reached 95%. Kuwait Project (Trade Hook Co.) - River Nile • Hassania Water Yard: Completion of civil works 100%. Commissioning and Handover is planned for next week. • Al Matama Hospital & Alababda Water Yard: Completion of civil works 100%. Commissioning and Handover is planned for next week. • Village 5 Water Yard: Completion of civil works 30%. • Gabati water yard: Completion of civil works 20 % . Civil Works for Rehabilitation and Provision of Solar System for 4 Water Yards in Sinnar State: * Completion 99 % of the solar system on 4 water yards. Only 3 signboards remain; they will be completed by Saturday.
21st Dec to 25th Dec | Kuwait Fund – Procurement Projects - Gedaref Contractor: Tihraga Engineering (2 sites) • Rehabilitation works at the Dalsa sites have reached 95%. Kuwait Project (Trade Hook Co.) - River Nile • Hassania Water Yard: Completion of civil works 100% and will be commissioned this week • Al Matama Hospital & Alababda Water Yard: Completion of civil works 100% and will be commissioned this week • Village 5 Water Yard: Finished casing work in borehole and ready for pumping test / 30% civil works. • Gabati water yard: Completion of civil works 70 %. Civil Works for Rehabilitation and Provision of Solar System for 4 Water Yards in Sinnar State: • Completion 100 % of the solar system on 4 water yards.
28th Dec to 31st Dec | Kuwait Fund – Procurement Projects - Gedaref Contractor: Tihraga Engineering for Building Co. (2 sites) • Rehabilitation works at two sites in Dalse reached 95% and are ready for handover. Kuwait Project (Trade Hook Co.) - River Nile • Al Matama Hospital & Alababda Water Yard: Completion of civil works 100% and the system was tested and commissioned. • Hassania Water Yard: Completion of civil works 100% and will be commissioned next week • Village 5 Water Yard: Finished casing work in borehole and ready for pumping test / 50% civil works. • Gabati water yard: Completion of civil works 75 %. 3. Provision of Solar Systems for 4 Water Yards in Sinnar State: • Technicians and three water committees were trained in three locations in Sinja and the Jalqani area on the operation and maintenance of solar systems.
4th Jan to 8th Jan | Kuwait Fund – Procurement Projects - Gedaref Contractor: Tihraga Engineering for Building Co. (2 sites) • Rehabilitation works at two sites in Dalse reached 95% completion; ready for handover. OLD Kuwait Project (Trade Hook Co.) – 4 sites - River Nile • Al Matama Hospital & Alababda Water Yard: 100% Completion of civil works of and the system was tested and commissioned. • Hassania Water Yard: 100% Completion of civil works and the system was tested and commissioned • Village 5 Water Yard: 70% completion of civil works. • Gabati water yard: 80 % Completion of civil works, Finished installation of the surface pump 3- Provision of Solar Systems for Four (4) Water Yards in Sinnar State: • Coordination was undertaken with the State Water Authority and the Water Stations Committee to organize a training workshop.
11th Jan to 15th Jan | Kuwait Fund – Procurement Projects Contractor: Tihraga Engineering for Building Co. (2 sites) • 2 borehole wells sites at Dalse have reached 95% of the rehabilitation. Ready to be handed over. OLD Kuwait Project (Trade Hook Co.) – 4 sites - River Nile • Al Matama Hospital & Alababda Water Yard: 100% Completion of civil works of and the system was tested and commissioned. • Hassania Water Yard: 100% Completion of civil works and the system was tested and commissioned • Village 5 Water Yard: 80% completion of civil works. Finished installation of the fence and the solar mounting structure. • Gabati water yard: 85 % Completion of civil works, Finished installation of the piping works Old Kuwait-Funded Project – Sennar State: • The supply of materials for three water yards was completed (100%). • The State Water Authority decided to postpone the planned training workshop due to the current security situation in Sinja. Old Kuwait-Funded Project – Al Jazirah State: • Drilling of the eighth well in the Isakn area was successfully completed. • Project materials were delivered to all designated sites. • Drilling works commenced one site at the Arkawit area. • Geophysical studies for four sites were completed.
18th Jan to 22nd Jan | OLD Kuwait Project (Trade Hook Co.) – 4 sites • Al Matama Hospital & Alababda Water Yard: 100% Completion of civil works of and the system was tested and commissioned. • Hassania Water Yard: 100% Completion of civil works and the system was tested and commissioned • Village 5 Water Yard: 100% completion of civil works. • Gabati water yard: 85 % Completion of civil works, Al Gazira State – Old Kuwait-Funded Project Fadqouba Area • Borehole drilling works: 10% • Supply and installation of steel fence: 15% Arkawit Area • Borehole drilling works: 100% • Supply and installation of steel fence: 35% Mustafa Idris Area • Setting out for the foundation of the elevated tank: 100% Umm Digarsi Area • Reinforced concrete (R.C.) works for the elevated tank foundation: 100% • Supply and installation of steel fence: 100% Isakn Area • Borehole drilling works: 80% • Steel fence installation: 45% Al-Halilah Village • Civil works and steel fence installation: 100% completed Sennar State – Old Kuwait-Funded Project Training Workshop • Concept note for the training of technicians and Water Committee has been submitted for approval. Elmasoudia Area • Borehole drilling works: 10% • Excavation for the steel elevated water tank foundation: 40% • Setting out of strip foundation for the security room: 100% Azaza and Bargo Areas • Installation of 6-inch HDPE water pipeline: 30% Elramash Area • Overall civil works completion: 94% • Major activities including initial electrical installations: 100% • Steel boundary fencing and backfilling in the water yard area: 80%
25th Jan to 29th Jan | OLD Kuwait Project (Trade Hook Co.) – 4 sites • Al Matama Hospital & Alababda Water Yard: 100% Completion of civil works of and the system was tested and commissioned. • Hassania Water Yard: 100% Completion of civil works and the system was tested and commissioned • Village 5 Water Yard: 100% completion of civil works. the system was tested and commissioned • Gabati water yard: 90 % Completion of civil works, OLD KUWAIT - Gazira & Sinnar States: Fadqouba Area • Borehole drilling works: 50% • Supply and installation of steel fence: 50% Arkawit Area • Excavation for foundation of elevated tank 100% • Borehole Drilling works 25% Mustafa Idris Area • Steel Fence installation 15% • Excavation for foundation of elevated tank 50% Umm Digarsi Area • Steel Structure works for elevated tank 50% Iskan Area • Borehole drilling works: 90% • Steel fence installation: 100% • Rehabilitation of the elevated water tank 95% Al-Halilah Village • Steel Structure works for elevated tank 50% Sennar State – Old Kuwait-Funded Project Overall work completion for the targeted areas is 42%.
1st Feb to 5th Feb | Kuwait Fund – Procurement Projects Contractor: Tihraga Engineering for Building Co. (2 sites) • Rehabilitation of two borehole wells in Dalse has reached 98% and is ready for handover. OLD Kuwait Project (Trade Hook Co.) – 4 sites - River Nile • Al Matama Hospital & Alababda Water Yard: 100% Completion of civil works of and the system was tested and commissioned. • Hassania Water Yard: 100% Completion of civil works and the system was tested and commissioned • Village 5 Water Yard: 100% completion of civil works. the system was tested and commissioned • Gabati water yard: 100 % Completion of civil works, the system was tested and commissioned Old Kuwait Project – Al Gezira State • Construction, solarization of 3 new water yards, and rehabilitation of 5 water yards are ongoing, with overall progress at 20% across all targeted locations. • A concept note for capacity building of local authorities has been submitted for review & approval. • A training workshop for 8 communities on water and solar technologies has been submitted for approval. Old Kuwait Project – Sinnar State • Construction, solarization, and rehabilitation of water yards are progressing, with overall completion at 50% in the targeted areas. • A training workshop for 7 communities on water and solar technologies has been submitted for approval.
8th Feb to 12th Feb | Kuwait Project - River Nile: • Preparations for the WUA training workshop and the handover of the four rehabilitated water yards are currently underway • Drilling of the two new water yards is progressing well; drilling has been completed at one site and has now started at the second. Old Kuwait Project – Al Gezira State • Construction, solarization of 3 new water yards, and rehabilitation of 5 water yards are ongoing, with overall progress at 70% across all targeted locations. • A concept note for capacity building of local authorities, reviewed & approved. • The concept note for a training workshop on water and solar technologies for 8 communities has been approved. -> The Bill of Quantities (BOQ) for technicians’ and engineers’ tools has been submitted for review and approval. Old Kuwait Project – Sinnar State • Construction, solarization, and rehabilitation of water yards are progressing, with overall completion at 55% in the targeted areas. • The Bill of Quantities (BOQ) for the technicians' and engineers' tools & training workshop, submitted for review.
15th Feb to 19th Feb | Kuwait Fund – Procurement Projects - Gedaref Contractor: Tihraga Engineering for Building Co. (2 sites) • Borehole wells No.1 site at Dalse have reached 100% of the rehabilitation. Ready for handover • Borehole wells No.11 site at Dalse have reached 100% of the rehabilitation. Ready for handover Kuwait Project - River Nile • Preparations ongoing for WUA training and handover of four rehabilitated water yards. • Drilling of two new water yards Hewa Co.) progressing well: • Sawarda water yard: Drilling and casing work have been completed, and they are now installing the elevated water tank. • Om Bashim water Yard: Drilling work have been completed, and casing works have commenced Old Kuwait Project – Al Gezira State • Construction, solarization of 3 new water yards, and rehabilitation of 5 water yards are ongoing, with overall progress at 73% across all targeted locations. • PCA for capacity building of local authorities has been approved, documents submitted to finance to create the invoice in the system. Old Kuwait Project – Sinnar State • Construction, solarization, and rehabilitation of water yards are progressing, with overall completion at 69% in the targeted areas. • A training workshop for 7communities on water and solar technologies has been approved, document shared with finance to create the invoice in the system.
22nd Feb to 26th Feb
1st Mar to 5th Mar | Kuwait Project • Preparations ongoing for WUA training and handover of four rehabilitated water yards. Construction of two wasteyards:(Hewa Co.): • Sawarda: 35% progress; Drilling and pumping tests have been completed, and work is now underway on the elevated water tank. • Om Bashim: 35% progress; Drilling and pumping tests have been completed, and work is now underway on the elevated water tank. Old Kuwait Project – Al Gezira State • Construction and solarization of three (3) new water yards, as well as rehabilitation of five (5) water yards, are ongoing. Overall progress has reached 79% across all targeted locations. • In coordination with the Water Corporation, a training workshop for the relevant authorities is scheduled for next week. Old Kuwait Project – Sinnar State • Construction, solarization, and rehabilitation of water yards are progressing well, with overall completion reaching 80% in the targeted areas.
8th Mar to 12th Mar | Kuwait Fund – Procurement Projects Contractor: Tihraga Engineering for Building Co. (2 sites) • Borehole wells No.1 site at Dalse have reached 100% of the rehabilitation. Ready for handover • Borehole wells No.11 at Dalse have reached 100% of the rehabilitation. Ready for handover
15th Mar to 19th Mar | Old Kuwait Project – Al Gezira State • Construction and solarization of three (3) new water yards, and rehabilitation of five (5) water yards,progress has reached 85% across all targeted locations. • 50 Community Water and Solar Technicians trained on Sustainability and Cost Recovery Systems, for 8 communities. Old Kuwait Project – Sinnar State • Construction, solarization, and rehabilitation of water yards are progressing well, with overall completion reaching 88% in the targeted areas.
22nd Mar to 26th Mar | Kuwait Project - Gedaref: • Preparations ongoing for WUA training and handover of four rehabilitated water yards. Construction of two wasteyards:(Hewa Co.): • Sawarda: 45% progress; works are now underway on the elevated water tank. Solar mounting structure and fencing. • Om Bashim: 40% progress; work is now underway on casting elevated water tank foundation Old Kuwait Project – Al Gezira State # Construction and solarization of three (3) new water yards, along with the rehabilitation of five (5) existing water yards, has been successfully completed. Overall progress has reached 100% across all targeted locations. Old Kuwait Project – Sinnar State # Construction, solarization, and rehabilitation of water yards have been completed, with 100% completion achieved in the targeted areas. # A training workshop for community water committees, water technicians, and solar systems was conducted on March 30–31, in coordination with the Sennar State Water Authority.
29th Mar to 2nd Apr | Kuwait Project - River Nile: • WUA training workshop was Conducted, handover of four rehabilitated water yards will start this week. • Construction of two water yards:(Hewa Co.): 1- Sawarda: 85% progress. The system will be ready for testing and commissioning this week 2- Om Bashim: 85% progress. The system will be ready for testing and commissioning this week Old Kuwait Project – Al Gezira State • Construction and solarization of three (3) new water yards, along with the rehabilitation of five (5) existing water yards, have been successfully completed. • Overall progress has reached 100% across all targeted locations. • Arrangements are currently being made with the Water Authority, local authorities in Kamleen and Hasasahya, and the targeted communities for project handover, scheduled for next week. Old Kuwait Project – Sinnar State • Construction, solarization, and rehabilitation of water yards have been officially handed over to the Sinnar State Water Authority and the project beneficiary communities. • A training workshop for a total of 51 people of community water committees, water technicians, and solar energy systems was successfully conducted from March 30–31, in coordination with the Sinnar State Water Authority. • A total of ,27 members of water user committees, 18 technicians, and 6 engineers were trained. Old Kuwait Fund – Procurement Projects - Gedaref Contractor: Tihraga Engineering for Building Co. • Boreholes No. 1 and No. 11 are completed and connected to the Dalasa water yard, now supplying water to the town.

## WaterSites
State | Locality | Location of the water station | Type of Water Intervention | Site Coordinates | Expected Drawdown (m) | Pumping Setting Depth (F) | Pump Selection Type & Model | Pump rated Power (kW) | Solar Array Power (kWp) | Number of Panels | N. of hours it operates on solar system for borehole | Water production rate per hour | Water productivity rate (m³/day) of the borehole | Water productivity per liter/day | Number of beneficiaries of water stations (persons) | Status | Ready for Handover | Handed Over | Handover Date
Sennar | Singa | Elseherg Area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N13.149135 E33.935121 | 1 | 200 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 70 | 560 | 560000 | 11200 | 100% | 2026-02-04 | Yes | 2025-12-30
Sennar | Singa | Elsalam Area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N13.129788 E33.941266 | 0.97 | 400 | DAB-SS6C 03-2inch | 7.5kw | 11 kWp | 16 | 8 | 30 | 240 | 240000 | 4800 | 100% | 2026-02-04 | Yes | 2025-12-30
Sennar | Singa | Block 150 | Rehabilitate, upgrade, and solarize existing non-functional water yards | N13.126113 E33.922401 | 0.87 | 350 | DAB-SS6C 25-2inch | 7.5kw | 11 kWp | 16 | 8 | 25 | 200 | 200000 | 4000 | 100% | 2026-02-04 | Yes | 2025-12-30
Sennar | Abu Hajar | Galgani Area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N12.444219 E34.227641 N12.444204 E34.227563 | 1.4 0.9 | 300 320 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 32 | 8 | 69 | 552 | 552000 | 11040 | 100% | 2026-02-04 | Yes | 2025-12-30
Sennar | Singa | Village Elmasoudia | Construct and solarize new Water Yards | N 13.1888163 E33.882024 | 0.85 | 400 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 34 | 272 | 272000 | 5440 | 100% | 2026-02-04 | Yes | 2026-01-04
Sennar | Singa | Village Elramash | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 13.2570107 E33.879532 | 1.12 | 350 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 35 | 280 | 280000 | 5600 | 100% | 2026-02-04 | Yes | 2026-01-04
Sennar | Singa | Wad Al-Abbas | New water network construction | N 13.1345457 E33.922779 | 1850 ML | PIPELINES | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 45 | 360 | 360000 | 7200 | 100% | 2026-02-04 | Yes | 2026-01-04
Gazira | Al Kamlin | Fadqouba Area | Construct and solarize new Water Yards | N15.073716 E32.784898 | 0.8 | 700 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 29 | 232 | 232000 | 4640 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Hasahisa | Arkawit Area | Construct and solarize new Water Yards | N13.129788 E33.941266 | 1.2 | 500 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | S | 35 | 280 | 280000 | 5600 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Hasahisa | Alribea Area | Construct and solarize new Water Yards | N14.991021 E32.808842 | 0.78 | 650 | DAB-SS6C 4-3inch | 7.5kw | 11 kWp | 16 | 8 | 28 | 224 | 224000 | 4480 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Hasahisa | Sha'edin area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N14.55047 E33.286893 | 0.6 | 450 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 32 | 8 | 40 | 320 | 320000 | 6400 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Hasahisa | Mustafa Idris Area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 15.073716 E32.842899 | 0.9 | 400 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 30 | 240 | 240000 | 4800 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Al Kamlin | Umm Digarsi Area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 14.996434 E33.227451 | 1 | 430 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 33 | 264 | 264000 | 5280 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Al Kamlin | Al-Halilah Village | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 15.101357 E33.173093 | 0.65 | 400 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 41 | 328 | 328000 | 6560 | 100% | 20/04/2026 | Yes | 31/03/2026
Gazira | Greater Medani | Alsakn Area | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 14.4261422 E33.618002 | 1.3 | 370 | DAB-SS6C 04-3inch | 7.5kw | 11 kWp | 16 | 8 | 29 | 232 | 232000 | 4640 | 100% | 20/04/2026 | Yes | 31/03/2026
River Nile | Ad-Damer | Alsayal/ Bashim Area | Construct and solarize new Water Yards | N17 33 33 E 33 51 57 | 1 | 510 | NOVA -Brand NSP14A-3inch | 7.5kw | 11.36 kWp | 16 | 8 | 30 | 240 | 240000 | 1000 | 100% |  | Yes | 2026-03-31
River Nile | Almatama | Alsawarid Area | Construct and solarize new Water Yards | N:16.779146 E: 33.543268 | 1 | 450 | NOVA -Brand NSP14A-3inch | 7.5kw | 11.36 kWp | 16 | 8 | 30 | 240 | 240000 | 2500 | 100% |  | Yes | 2026-03-31
River Nile | Ad-Damer | Gabati | Rehabilitate, upgrade, and solarize existing non-functional water yards | N: 17.197896 E: 33.760118 | - | Surface pumps | Caprari -826731/1 (23-58 L/s- 100 m head) | 55 KW - Electric pump 2*7.5 kW - Solar Pump | 17.04 kWp | 24 | 8 | 82.8 | 662.4 | 662000 | 11000 | 100% |  | Yes | 2016-03-30
River Nile | Almatama | Almatama Hospital | Rehabilitate, upgrade, and solarize existing non-functional water yards | N: 16.719635 E: 33.366085 | 2 | 40 | 10 HP | 7.5kw | 11.36 kWp | 16 | 8 | 30 | 180 m3/day | 180000 | 2000 | 100% |  | Yes | 2016-03-30
River Nile | Ad-Damer | Hassania Alrihid | Rehabilitate, upgrade, and solarize existing non-functional water yards | N: 17.458311 E: 33.807184 | - | - | - | 7.5kw | 11.36 kWp | 16 | 8 | 30 | 180 | 180000 | 2000 | 100% |  | Yes | 2026-03-31
River Nile | Ad-Damer | Almnasir village 5 | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 17.466898 E33.995114 | 1.5 | 590 | Shakti 115 m Head | 15 kW | 21.3 kWp | 30 | 8 | 30 | 180 | 180000 | 9000 | 100% |  | Yes | 2026-03-31
Gedaref | El Guresha | Barbar Elfugra | Construct and solarize new Water Yards | N 13.644320 - E 36.139440 | [10 empty] | 5000 | 3%
Gedaref | Gedaref town | Dalase Bore 1 | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 14.027389 - E 35.428257 | 4.17 | 102 | Metro 95MR8 N/13 | 2.2 KW - 3HP |  | 14 | 6 | 7.2 | 40 | 40000 | 9000 | 100% | Yes
Gedaref | Wasat Elgedaref | Dalase Bore 2 | Rehabilitate, upgrade, and solarize existing non-functional water yards | N 14.025338 - E 35.422123 | 1.6 | 106.5 | Metro 95MR8 N/13 | 2.2 KW - 3HP |  | 14 | 6 | 5m | 30 | 30000 | 8000 | 100% | Yes
[14 empty] | 2464000 | 49280
Note on T1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Yahya Mohammed @Alaa Belal @Mustafa Hassan @Ahmed Adam please complete this information for sites handed over under Kuwait-447
Note on P17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Yahya Mohammed Please fill out for water sites under old kuwait based on water output cc: @Alaa Belal Reply: Done
Note on Q23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Yassir Zahir / @Ahmed Adam please fill in the percentage of completion

## WUAs
No. | State | Locality | Community | Name | Gender | Age | Type of Support | JointProgram | Cross-Pillar | SupportProject | YearofSupport
1 | Sennar | Sinja | Al-Masoudiya Village | Al-Daw Mohammed Zein Ahmed | Male | 42 | Drinking Water | No | No | Kuwait-447 | 2026
2 | Sennar | Sinja | Al-Masoudiya Village | Nasriya Mohammed Musa | Female | 40 | Drinking Water | No | No | Kuwait-447 | 2026
3 | Sennar | Sinja | Al-Masoudiya Village | Jawahir Muhammad Hamid | Female | 37 | Drinking Water | No | No | Kuwait-447 | 2026
4 | Sennar | Sinja | Al-Ramash villages | Khalil Al-Sayed Ahmed | Male | 38 | Drinking Water | No | No | Kuwait-447 | 2026
5 | Sennar | Sinja | Al-Ramash villages | Sawsan Othman Mohammed | Female | 41 | Drinking Water | No | No | Kuwait-447 | 2026
6 | Sennar | Sinja | Al-Ramash villages | Hawa Abdelrahman Idris | Female | 36 | Drinking Water | No | No | Kuwait-447 | 2026
7 | Sennar | Sinja | Block 150 | Afif Mohammed Noum | Male | 42 | Drinking Water | No | No | Kuwait-447 | 2026
8 | Sennar | Sinja | Block 150 | Hasib Yahya Ali | Male | 35 | Drinking Water | No | No | Kuwait-447 | 2026
9 | Sennar | Sinja | Block 150 | Shahrzar Muhammad Haballah | Female | 32 | Drinking Water | No | No | Kuwait-447 | 2026
10 | Sennar | Sinja | Al-Salam Neighborhood | Hamdan Ahmed Ibrahim | Male | 36 | Drinking Water | No | No | Kuwait-447 | 2026
11 | Sennar | Sinja | Al-Salam Neighborhood | Suwamer Al-Nazir Hassan | Female | 33 | Drinking Water | No | No | Kuwait-447 | 2026
12 | Sennar | Sinja | Al-Salam Neighborhood | Mahasin,Abdelrahim MohAmmed | Female | 31 | Drinking Water | No | No | Kuwait-447 | 2026
13 | Sennar | Sinja | Barqo Wad Al-Abbas Block 166 | Abdelrahman Toto Daldoum | Male | 47 | Drinking Water | No | No | Kuwait-447 | 2026
14 | Sennar | Sinja | Barqo Wad Al-Abbas Block 166 | Ezzeldin OthmanAli | Male | 34 | Drinking Water | No | No | Kuwait-447 | 2026
15 | Sennar | Sinja | Barqo Wad Al-Abbas Block 166 | Mahla Ibrahim Ali | Female | 37 | Drinking Water | No | No | Kuwait-447 | 2026
16 | Sennar | Sinja | ALusharjet | Qasim Ahmed Ibrahim | Male | 38 | Drinking Water | No | No | Kuwait-447 | 2026
17 | Sennar | Sinja | ALusharjet | Banqa Muhammad Al | Male | 38 | Drinking Water | No | No | Kuwait-447 | 2026
18 | Sennar | Sinja | ALusharjet | Ashraf Al-Taher | Male | 40 | Drinking Water | No | No | Kuwait-447 | 2026
19 | Sennar | Sinja | Jalqani village | Bashir Al-Nour Bakhit | Male | 54 | Drinking Water | No | No | Kuwait-447 | 2026
20 | Sennar | Sinja | Jalqani village | Siddig Abdel Shard Siddig | Male | 46 | Drinking Water | No | No | Kuwait-447 | 2026
21 | Sennar | Sinja | Jalqani village | Hussein Othman Mohammed Saeed | Male | 42 | Drinking Water | No | No | Kuwait-447 | 2026
22 | Al Jazeera | Al-Hasahisa | Al-Rbah village | Rashid Suleiman | Male | 44 | Drinking Water | No | No | Kuwait-447 | 2026
23 | Al Jazeera | Al-Hasahisa | Al-Rbah village | Idris Haroun | Male | 47 | Drinking Water | No | No | Kuwait-447 | 2026
24 | Al Jazeera | Al-Hasahisa | Al-Rbah village | Mohammad Fadl Al-Sayyid | Male | 50 | Drinking Water | No | No | Kuwait-447 | 2026
25 | Al Jazeera | Al-Hasahisa | Al-Rbah village | Fakhr Al-Din Zarqan | Male | 45 | Drinking Water | No | No | Kuwait-447 | 2026
26 | Al Jazeera | Al-Kamilin locality | Umm Daqrasi village | Emad Al-Junaid | Male | 39 | Drinking Water | No | No | Kuwait-447 | 2026
27 | Al Jazeera | Al-Kamilin locality | Umm Daqrasi village | Mohammad Hassan Muhammad | Male | 41 | Drinking Water | No | No | Kuwait-447 | 2026
28 | Al Jazeera | Al-Kamilin locality | Umm Daqrasi village | Haider Al-Amin | Male | 46 | Drinking Water | No | No | Kuwait-447 | 2026
29 | Al Jazeera | Al-Kamilin locality | Umm Daqrasi village | Aref Mustafa | Male | 42 | Drinking Water | No | No | Kuwait-447 | 2026
30 | Al Jazeera | Al-Kamilin locality | Al-Halila village | Najm al-Din Ahmad Muhammad | Male | 29 | Drinking Water | No | No | Kuwait-447 | 2026
31 | Al Jazeera | Al-Kamilin locality | Al-Halila village | Lutfi Jad Karim Hamad | Male | 39 | Drinking Water | No | No | Kuwait-447 | 2026
32 | Al Jazeera | Al-Kamilin locality | Al-Halila village | Muzammil Muhammad Mahmoud | Male | 45 | Drinking Water | No | No | Kuwait-447 | 2026
33 | Al Jazeera | Al-Kamilin locality | Fadoqouba village | Othman Ahmed Omar | Male | 37 | Drinking Water | No | No | Kuwait-447 | 2026
34 | Al Jazeera | Al-Kamilin locality | Fadoqouba village | Abdulmonem Ibrahim Dhu Al-Nun | Male | 37 | Drinking Water | No | No | Kuwait-447 | 2026
35 | Al Jazeera | Al-Kamilin locality | Fadoqouba village | Mohamed Gadallah Taha | Male | 49 | Drinking Water | No | No | Kuwait-447 | 2026
36 | Al Jazeera | Al-Hasahisa | Idris Mustafa Village | Shawqi Qasim Al-Fadil Ahmed | Male | 44 | Drinking Water | No | No | Kuwait-447 | 2026
37 | Al Jazeera | Al-Hasahisa | Idris Mustafa Village | Abdullah Sheikh Idris | Male | 41 | Drinking Water | No | No | Kuwait-447 | 2026
38 | Al Jazeera | Al-Hasahisa | Arkawit neighborhood | Jalal al-Din al-Qurashi | Male | 42 | Drinking Water | No | No | Kuwait-447 | 2026
39 | Al Jazeera | Al-Hasahisa | Arkawit neighborhood | Muhammad Ibrahim Muhammad | Male | 47 | Drinking Water | No | No | Kuwait-447 | 2026
40 | Al Jazeera | Al-Hasahisa | Arkawit neighborhood | Farouk Al-Amin Mustafa | Male | 48 | Drinking Water | No | No | Kuwait-447 | 2026
41 | Al Jazeera | Al-Hasahisa | Arkawit neighborhood | Faisal Jamaa | Male | 46 | Drinking Water | No | No | Kuwait-447 | 2026
42 | Al Jazeera | Al-Hasahisa | Sha'a Al-Din Village | Nasr al-Din Abd al-Rahman Muhammad | Male | 34 | Drinking Water | No | No | Kuwait-447 | 2026
43 | Al Jazeera | Al-Hasahisa | Sha'a Al-Din Village | Mutawakkil Ahmad Fadl Al-Mawla | Male | 37 | Drinking Water | No | No | Kuwait-447 | 2026
44 | Al Jazeera | Wad Madani | Alsakn Area | Muhtadi Al-Sunni | Male | 42 | Drinking Water | No | No | Kuwait-447 | 2026
45 | Al Jazeera | Wad Madani | Alsakn Area | Mirghani Mahmoud | Male | 44 | Drinking Water | No | No | Kuwait-447 | 2026
46 | Al Jazeera | Wad Madani | Alsakn Area | Tanqa Muhammad | Male | 39 | Drinking Water | No | No | Kuwait-447 | 2026
47 | River Nile | Al-matma | ALSAWARD | Amaer osaman al-alem | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
48 | River Nile | Al-matma | ALSAWARD | Nagi abdallah mohammed ahmed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
49 | River Nile | Al-matma | ALSAWARD | Murtada bader saad | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
50 | River Nile | Al-matma | ALSAWARD | Ezzaldeen abdalhadi | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
48 | River Nile | Al-matma | ALSAWARD | Mohammed salih rahmtallah | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
49 | River Nile | Al-matma | ALSAWARD | Abd-alghdeer alma'amuon ahmed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
50 | River Nile | Al-matma | ALSAWARD | Abdalmoun'm ahmed mohammed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
51 | River Nile | Al-matma | ALSAWARD | Mohammed abdalseed mohammed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
52 | River Nile | Al-matma | ALSAWARD | Dar algalal mahjoub | Female |  | Drinking Water | No | No | Kuwait-447 | 2026
53 | River Nile | Al-matma | ALSAWARD | Mustafa bader sa'ad | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
54 | River Nile | Al-matma | ALSAWARD | Yassmen hassan khalf allah | Female |  | Drinking Water | No | No | Kuwait-447 | 2026
55 | River Nile | Al-matma | ALSAWARD | Al-samani AL-saeed al-samani | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
56 | River Nile | Al-matma | ALSAWARD | Amir osman ali hammed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
57 | River Nile | Al-matma | ALIA HOSPITAL | Mohammed sadeeq | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
58 | River Nile | Al-matma | ALIA HOSPITAL | Sanhuory isa'a | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
59 | River Nile | Al-matma | ALIA HOSPITAL | Ali mohammed ali | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
60 | River Nile | Al-matma | ALIA HOSPITAL | Ali mohammed salih | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
61 | River Nile | Al-matma | ALIA HOSPITAL | Muntaser khalf allah | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
62 | River Nile | Ad-Damer | QABATI | Abaas haasan abaas | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
63 | River Nile | Ad-Damer | QABATI | Abod moahhmed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
64 | River Nile | Ad-Damer | QABATI | Salah mohammed al-mardi | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
65 | River Nile | Ad-Damer | QABATI | Al-tayeb abdallah | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
66 | River Nile | Ad-Damer | QABATI | Ahmed babiker | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
67 | River Nile | Ad-Damer | QABATI | nouraldeen ahmed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
68 | River Nile | Ad-Damer | QABATI | Ahmed al-seed ali | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
69 | River Nile | Ad-Damer | QABATI | Akram mohammed dafallah | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
70 | River Nile | Ad-Damer | QABATI | Insaf abdalghani | Female |  | Drinking Water | No | No | Kuwait-447 | 2026
71 | River Nile | Ad-Damer | VILLAG 5 | Ibrahim hassan salih ali | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
72 | River Nile | Ad-Damer | VILLAG 5 | Abd alhamid hasssan | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
73 | River Nile | Ad-Damer | VILLAG 5 | Khalid hamed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
74 | River Nile | Ad-Damer | VILLAG 5 | Samer mohammed ahmed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
75 | River Nile | Ad-Damer | VILLAG 5 | Yahia ibrahim hassan | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
76 | River Nile | Ad-Damer | VILLAG 5 | Mohammed ahmed khider | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
77 | River Nile | Ad-Damer | VILLAG 5 | Abd algodous mohammed suliman | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
78 | River Nile | Ad-Damer | AL-SAyAL | Mohammed omer dafalseed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
79 | River Nile | Ad-Damer | AL-SAyAL | Osman fadal-mula | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
80 | River Nile | Ad-Damer | AL-SAyAL | Ghulam-Aldeen mohammed omer | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
81 | River Nile | Ad-Damer | AL-SAyAL | Mohammed ali salih | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
82 | River Nile | Ad-Damer | AL-SAyAL | Osman Al-Abed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
83 | River Nile | Ad-Damer | AL-REHID | Abdo ali idris | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
84 | River Nile | Ad-Damer | AL-REHID | Abdallah mansour | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
85 | River Nile | Ad-Damer | AL-REHID | Hamed mansour mohammed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
86 | River Nile | Ad-Damer | AL-REHID | Bala saeed salih | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
87 | River Nile | Ad-Damer | AL-REHID | Alomda awad alseed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
88 | River Nile | Ad-Damer | AL-REHID | Hassan abdalghader ragb | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
89 | River Nile | Ad-Damer | AL-REHID | Alabd balola ala'as | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
90 | Gedaref | Elguresha | Barbar Elfugra | Abdalla Ibrahim Yahya | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
91 | Gedaref | Elguresha | Barbar Elfugra | Adam Ishaq Dahiya | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
92 | Gedaref | Elguresha | Barbar Elfugra | Alkhair Bakheit Mohamed | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
93 | Gedaref | Elguresha | Barbar Elfugra | Dafalla Abdalla Adam | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
94 | Gedaref | Elguresha | Barbar Elfugra | Mohamed Mahmod Rajlein | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
95 | Gedaref | Gedaref Town | Dalasa 1 | Ezeldeen Abdalla Aljack | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
96 | Gedaref | Gedaref Town | Dalasa 1 | Younis Ibrahim Aljak Alebaid | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
97 | Gedaref | Gedaref Town | Dalasa 1 | Abdalla Sirelkhatim Babiker | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
98 | Gedaref | Gedaref Town | Dalasa 1 | Alhasab Ahmed Mohamed Abdalla | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
99 | Gedaref | Gedaref Town | Dalasa 1 | Sabil Abakar Mursal Dod | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
100 | Gedaref | Gedaref Town | Dalasa 1 | Ali Ahmed Maala Adam | Male |  | Drinking Water | No | No | Kuwait-447 | 2026
101 | Gedaref | Gedaref Town | Dalasa 1 | Fadoul Nasir Abdulkarim | Male |  | Drinking Water | No | No | Kuwait-447 | 2026

## Toolkits
River Nile
2 sets for each Water Users Association (WUA), totaling 12 sets.
3 sets for the River Nile State Water Corporation (RNSWC)

## Locations
State | IP | Locality | Town/Community
Sennar | UNDP_RR | Singa | Elseherg Area
Sennar | UNDP_RR | Singa | Elsalam Area
Sennar | UNDP_RR | Singa | Block 150
Sennar | UNDP_RR | Abu Hajar | Galgani Area
Sennar | UNDP_RR | Singa | Village Elmasoudia
Sennar | UNDP_RR | Singa | Village Elramash
Sennar | UNDP_RR | Singa | Wad Al-Abbas
Gazira | UNDP_RR | Al Kamlin | Fadqouba Area
Gazira | UNDP_RR | Hasahisa | Arkawit Area
Gazira | UNDP_RR | Hasahisa | Alribea Area
Gazira | UNDP_RR | Hasahisa | Sha'edin area
Gazira | UNDP_RR | Hasahisa | Mustafa Idris Area
Gazira | UNDP_RR | Al Kamlin | Umm Digarsi Area
Gazira | UNDP_RR | Al Kamlin | Al-Halilah Village
Gazira | UNDP_RR | Greater Medani | Alsakn Area
River Nile | UNDP_RR | Al-Damer | Alsayal/ Bashim Area
River Nile | UNDP_RR | Al-Matama | Alsawarid Area
River Nile | UNDP_RR | Al-Damer | Gabati
River Nile | UNDP_RR | Al-Matama | Almatama Hospital
River Nile | UNDP_RR | Al-Damer | Hassania Alrihid
River Nile | UNDP_RR | Al-Damer | Almnasir village 5
Gedaref | UNDP_RR | El Guresha | Barbar Elfugra
Gedaref | UNDP_RR | Gedaref town | Dalase Bore 1
Gedaref | UNDP_RR | Wasat Elgedaref | Dalase Bore 2