## Project_FactSheet
Project Name: | Powering Sudan's Agriculture: Renewable Water Solutions for Sustainable Future
Award No: | Award No: 1527487 (457)
Donor: | Kuwait Fund for Arab Economic Development (KFAED) 013848
Total budget: | 2000000
Start date: | 2025-11-01
End date: | 2027-04-30
Duration: | 18 months
Target locations: | White Nile, Al Jazeera, Kassala, Red Sea
Implementing Partners: | NA
Last update to tracker: | 2026-03-18

## NKuwait_Tracker
Outcome | Output | Activity | Target | T_WhiteNile | WhiteNile_Actual | T_AlJazeera | AlJazeera_Actual | T_Kassala | Kassala_Actual | T_RedSea | RedSea_Actual | Actual_Total | Comment_18.03
To enhance agricultural productivity, water security, and rural livelihoods in Sudan through sustainable solar-powered irrigation, and improved water infrastructure for smallholder farmers. | Output 1: Improved Access to Affordable and Sustainable Water for Irrigation | Activity 1.1: Install 50 solar-powered water pumps of different capacity based on the existing irrigation structures for irrigation based on the feasibility assessment/study. | 50 | 14 | 10 | 30 | 10 | 3 | 0 | 3 | 0 |  | 10 in WN; 10 in Gazeera; identified and works ongoing
|  | Activity 1.2 Training of 500 small holder farmers on efficient water management techniques including Solar PV-Operation and Maintenance (O&M). | 500 | 140 |  | 300 |  | 30 |  | 30 |  |  | Training after the formation of the association; 10 will be trained in each association/water pump; each association has 10; due to size of water pump capacity, can only support 10-20 farmers
|  | Activity 1.3: Establish/reactivate 50 community-based water user associations varies depending on the existing schemes and farmers associations and cost recovery mechanisms to enhance sustainable and equitable water distribution and management. | 50 | 14 |  | 30 |  | 3 |  | 3 |  |  | Linked with solar pump; 1.1 which will be trained
| Output 2: Rehabilitated Irrigation Infrastructure for Sustainable Water Management | Activity 2.1: Conduct assessments to identify and prioritize small-scale irrigation infrastructure in need of rehabilitation. | 50 | 14 |  | 30 |  | 3 |  | 3 |  |  | Assessment done in November for 20 pumps and 8 canals; scale of impact area of damaged canals to revive maximum agricultural activity; led by Ministry of Agriculture & Irrigation
|  | Activity 2.2: Rehabilitate 28 existing (small) irrigation canals, storage facilities, and water distribution networks to enhance efficiency. | 28 | 11 |  | 14 |  | 3 |  | 3 |  |  | 11 done now in WN; 16 in procurement - pending cost estimation and based on which will be able to determine balance for revised target of canals

## Target_Associations
# | State | Locality | Location | GPS coordinates | Association name | Focal Point/ Chair of Association | FP's Phone Number | Farm Area (Feddan) | Number of Association members | Number of beneficiaries
1 | Al Jazeera | Alhasahesa | Amara Abied |  | Amara Abied | TajEldien Alshiekh | 0912632133/0128437025 | 10~15 | 580 |  | 15
2 | Al Jazeera | Alhasahesa | Arbeji |  | Arbeji | Ismaiel Altayib Alameen | 911328242 | 10~15 | 131 |  | 15
3 | Al Jazeera | Alhasahesa | Wad Alfadni |  | Khlaw Wad Alfadni | Alkhaliekha Mohammed Alrayh | 912381302 | 10~15 | 62 |  | 15
4 | Al Jazeera | Greater Madani | Al-danagla |  | Aldanagla Collaboration | Alfatih Babikr Alamien | 114225880 | 10~15 | 70 |  | 15
5 | Al Jazeera | Greater Madani | Fadasi |  | Fadasi for Vegateable | Izeldien Omar Ahmed | 916062473 | 10~15 | 70 |  | 15
6 | Al Jazeera | AlKamleen | Alkasmber |  | Kasamber | Mohammed Babikir Alameen | 912860263/0122323603 | 20~30 | 75 |  | 30
7 | Al Jazeera | AlKamleen | Al Bashagra |  | Al Bashagra Collaboration | Mustafa Eltayib | 917322341 | 20~30 | 180 |  | 30
8 | Al Jazeera | AlKamleen | Albageir |  | Collaboration for Friut& Vegateble | Bashier Suliman Ahmed | 0912455272/0113102852 | 20~30 | 2000 |  | 30
9 | Al Jazeera | Sourthen of Algazira | Diem Almashaikha |  | Diem Almashaikha | Mergani Alhaj Altoum | 969633336 | 20~30 | 224 |  | 30
10 | Al Jazeera | Sourthen of Algazira | Gendal |  | Gendal | Hamid Algasim Ahmed | 918081392/0123742249 | 20~30 | 364 |  | 30
11 | White Nile | Guli | Alhisi |  | Awllad Saadwen Agriculture | Tag Al-Asfia Hassan | 912271646 | 10~15 | 36 |  | 15
12 | White Nile | Guli | Guli |  | Al-amel Agriculture | Yagoub Mohamed | 923344409 | 10~15 | 30 |  | 15
13 | White Nile | Guli | Wad Shamam |  | Bashier Alkhier Agriculture | Ahmed Altieb Mahala | 966204853 | 10~15 | 49 |  | 15
14 | White Nile | Guli | Wad Shamam |  | Abna Mongash Agriculture | Ahmed Mohamed Musa | 912763627 | 10~15 | 20 |  | 15
15 | White Nile | Guli | Rodat Almokhtar |  | Bahsr Anied Agriculture | Abdelmajied Hassan Ibrahiem | 999908978 | 10~15 | 35 |  | 15
16 | White Nile | Ad-Dewaim | Almoselamb |  | Almoselamb Agriculture | Alzain Abdala Alobadi | 918049906 | 20~30 | 30 |  | 30
17 | White Nile | Ad-Dewaim | Almekefi |  | Almekefi Agriculture | Abelhafeez Mahmoud | 912491004 | 20~30 | 30 |  | 30
18 | White Nile | Ad-Dewaim | Um Lahum |  | Um Lahum Agriculture | Alkhir Hassan Khalifa | 913252529 | 20~30 | 30 |  | 30
19 | White Nile | Ad-Dewaim | Elmeneedrip |  | Elmeneedrip Agriculture | Basheer Abelrahim Ali | 963164309 | 20~30 | 30 |  | 30
20 | White Nile | Ad-Dewaim | Algardood |  | Algardood Agriculture | Hamud Ahmed Esmaeel | 912519401 | 20~30 | 30 |  | 30
4076
450
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sanaa Saeed / @Mustafa Hassan please make sure the changed association is updated. cc: @Yahya Mohammed Reply: Dear Marrian,Done
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I would put the two figures separately. e.g. in Diem Almashaikha the 30 feddans will only serve a limited number of poor families while the association has 1660 members. the vast majority of them are not targeted by the project. We can't inflate the number of beneficiaries based on association membership.
Note on J9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Sanaa Saeed / @Mustafa Hassan kindly advise if this number is accurate cc: @Yahya Mohammed / @Osama Tageldin Reply: Confirmed, the number is accurate as per the MoA report

## Weekly_Updates
Week | Update
28th Dec to 31st Dec | 5. New Kuwait Project: • A coordination meeting was held with the Ministry of Agriculture to identify locations for irrigation pumps. • Targeted locations were shared by the Ministry of Agriculture. N) White Nile State: Water initiative has officially commenced with the handover of 10 sites: • 8 sites for Nile pumps serving agricultural cooperatives • 2 sites for the rehabilitation of agricultural channels The companies on the ground have started implementing the project.
4th Jan to 8th Jan | New Kuwait Project (Hewa Co.) – 2 new water yards • The two sites (Alsawarda & Umm Bashim) have been handed over to the contractor. 4- New Kuwait-Funded Project - Gazira & Sinnar • The handover of agricultural irrigation pumps for ten (10) sites successfully completed. E) White Nile State: Water initiative has officially commenced with the handover of 10 sites: • 8 sites for Nile pumps serving agricultural cooperatives • 2 sites for the rehabilitation of agricultural channels The companies on the ground have started implementing the project.
11th Jan to 15th Jan | New Kuwait Project (Hewa Co.) – 2 new water yards - River Nile • the contractor conducted the geophysical study and started mobilizing the drilling rig and materials to the site 4- New Kuwait-Funded Project - Gazir & Sinanr • The handover of agricultural irrigation pumps for ten (10) sites successfully completed.
18th Jan to 22nd Jan | New Kuwait Project (Hewa Co.) – 2 new water yards • sites have been handed over to the contractor. And mobilization and preparation of the sites are ongoing New Kuwait-Funded Project – Al Gazira State • Samples of materials have been submitted for approval.
25th Jan to 29th Jan | New Kuwait Project (Hewa Co.) – 2 new water yards • Drilling rig will arrive today to the site and starts drilling next week. New Kuwait Project- Gazira State • Samples of materials have been approved.
1st Feb to 5th Feb | New Kuwait Project (Hewa Co.) – 2 new water yards - River Nile • Drilling rig arrived at the site and started drilling.
8th Feb to 12th Feb
15th Feb to 19th Feb
22nd Feb to 26th Feb
1st Mar to 5th Mar | New Kuwait Project • Provision of ten (10) solar agricultural pumps: the supplier has not yet commenced implementation activities.
8th Mar to 12th Mar | New Kuwait Project • Provision of ten (10) solar agricultural pumps: the supplier has not yet commenced implementation activities.
15th Mar to 19th Mar | New Kuwait Project - Powering Sudan's Agriculture: White Nile State: • Provision of ten (10) solar agricultural pumps: the Solar items have been transported to the state • Rehabilitation of 11 Canals: 86% completion of the civil work Gezira State: • Provision of ten (10) solar agricultural pumps: Road permit was issued to trasoport the solar items to state. • Rehabilitation of 16 Canals: under tendering process
22nd Mar to 26th Mar | • Joint meeting with the Ministry of Production was organized to discuss progress on the rehabilitation of 6 canals at the Gash Scheme • Cost for geophysical survey which was estimated at SDG 16M have been absorbed by State Government. • Joint meeting was convened with Minister of Agriculture to solicit Government support to expediate the process to start the canal rehabilitation. Government promised to absorb some of the cost. . New Kuwait Project # Provision of ten (10) solar agricultural pumps: the supplier has not yet commenced implementation activities. # Contractors completed site visits for bid preparation related to the South Gezira canal rehabilitation project on March 20.
29th Mar to 2nd Apr | Kuwait 2 Project • A joint engineering team from the Ministry of Agriculture and the Physical Infrastructure are currently finalizing plans to conduct geophysical surveys for the rehabilitation of 6 canals in Kassala State. New Kuwait Project • Provision of ten (10) solar agricultural pumps: The supplier has not yet commenced implementation activities.
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Yahya Mohammed there has been the exact same update for New Kuwait project all of March in the weekly updates.
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ahmed Adam 11+ 16 in procurement = 27

## WaterPumps
No. | State | Locality | Location of the water pump | Type of Water Intervention | Site Coordinates | Farm area (Feddan) | Pumping Setting Depth (F) | Pump Selection Type & Model | Nominal Solar Power (kWp) | Number of Panels | N. of hours it operates on solar system | Water production rate per hour ((m³/hr) | Water productivity rate (m³/day) | Number of beneficiaries of water stations (persons) | Status | Ready for Handover | Handed Over | Handover Date
1 | Gezira | Alhasahesa | Amara Abied | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/2 | 11.9 | 17 | 8 | 100 | 500 | 580 | on going
2 | Gezira | Alhasahesa | Arbeji | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/3 | 11.9 | 17 | 8 | 100 | 500 | 131 | on going
3 | Gezira | Alhasahesa | Wad Alfadni | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/4 | 11.9 | 17 | 8 | 100 | 500 | 62 | on going
4 | Gezira | Greater Madani | Al-danagla | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/5 | 11.9 | 17 | 8 | 100 | 500 | 70 | on going
5 | Gezira | Greater Madani | Fadasi | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/6 | 11.9 | 17 | 8 | 100 | 500 | 70 | on going
6 | Gezira | AlKamleen | Alkasmber | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 75 | on going
7 | Gezira | AlKamleen | Um-Dagrsi | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 180 | on going
8 | Gezira | AlKamleen | Albageir | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 2000 | on going
9 | Gezira | Sourthen of Algazira | Diem Almashaikha | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 224 | on going
10 | Gezira | Sourthen of Algazira | Gendal | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 364 | on going
11 | White Nile | Guli | Alhisi | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/2 | 11.9 | 17 | 8 | 100 | 500 | 36 | on going
12 | White Nile | Guli | Guli | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/3 | 11.9 | 17 | 8 | 100 | 500 | 30 | on going
13 | White Nile | Guli | Wad Shamam | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/4 | 11.9 | 17 | 8 | 100 | 500 | 49 | on going
14 | White Nile | Guli | Wad Shamam | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/5 | 11.9 | 17 | 8 | 100 | 500 | 20 | on going
15 | White Nile | Guli | Rodat Almokhtar | Solarized Irrigation Pump |  | 10~15 | N/A | PSK3-7 CS-G100-17/6 | 11.9 | 17 | 8 | 100 | 500 | 35 | on going
16 | White Nile | Ad-Dewaim | Almoselamb | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 30 | on going
17 | White Nile | Ad-Dewaim | Almekefi | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 30 | on going
18 | White Nile | Ad-Dewaim | Um Lahum | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 30 | on going
19 | White Nile | Ad-Dewaim | Elmeneedrip | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 30 | on going
20 | White Nile | Ad-Dewaim | Algardood | Solarized Irrigation Pump |  | 20~30 | N/A | PSK3-15 CS-G150-12.5/4,6 | 23.8 | 34 | 8 | 200 | 1000 | 30 | on going

## Canals
No. | State | Locality | Name of Canals | Site Coordinates | Length (m) | SOW | Amount of water flowing in the canals (M3) | Number of beneficiaries of water stations (persons) | Status | Ready for Handover | Handed Over | Handover Date
1 | White Nile | Guli | Dakhla main canal | 13.592920 N 32.498924 E | 4190 | Rehabilitation irrigation canals of Dakhla main channel |  |  | 100%
2 | White Nile | Guli | Dakhla canal1 | 13.563492 N 32.498465 E | 1300 | Rehabilitation irrigation canals of branch canal Al-Dakhla, 1 |  |  | 100%
3 | White Nile | Guli | Dakhla canal 2 | 13.579376 N 32.498351 E | 3000 | Rehabilitation irrigation canals of branch canal Al-Dakhla, 2 |  |  | 100%
4 | White Nile | Guli | Dakhla canal 3 | 13.558205 N 32.498500 E | 1280 | Rehabilitation irrigation canals of branch canal Al-Dakhla, 3 |  |  | 100%
5 | White Nile | Guli | Dakhla canal 4 | 13.591984 N 32.498705 E | 1680 | Rehabilitation irrigation canals of branch canal Al-Dakhla, 4 |  |  | 100%
6 | White Nile | Guli | Safa Main canal | 13.620988 N 32.525441 E | 7974 | Rehabilitation irrigation canals of Al-Safa, main channel |  |  | 100%
7 | White Nile | Guli | Safa canal 1 | 13.588257 N 32.496598 E | 2020 | Rehabilitation irrigation canals of branch canal Al-Safa, 1 |  |  | 100%
8 | White Nile | Guli | Safa canal 2 | 13.576706 N 32.484732 E | 1800 | Rehabilitation irrigation canals of branch canal Al-Safa, 2 |  |  | 100%
9 | White Nile | Guli | Safa canal 3 | 13.571250 N 32.484653 E | 1790 | Rehabilitation irrigation canals of branch canal Al-Safa, 3 |  |  | 100%
10 | White Nile | Guli | Safa canal 4 | 13.574022 N 32.484747 E | 1610 | Rehabilitation irrigation canals of branch canal Al-Safa, 4 |  |  | 100%
11 | White Nile | Guli | Safa canal 5 | 13.574109 N 32.484754 E | 700 | Rehabilitation irrigation canals of branch canal Al-Safa, 5 |  |  | 100%
12 | Kassala | Kassala | Fota Canal | N 15,3021.54 E 36,2129.78 | 1100 | Rehablitation Irrigation Canal |  |  | 100%
13 | Kassala | Kassala | Makaly Canal | N 15,4036.47 E 36,2015.05 | 4100 | Rehablitation Irrigation Canal |  |  | 100%
32544
32.544
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Yahya Mohammed the canals being rehabilitated are in Al-Qutaynah not Guli. Please confirm. cc @Mustafa Hassan