## Project_FactSheet
Project Name: | Strengthening the Resilience of IDPS, Refugees and Vulnerable Host Communities in East Sudan
Award No: | 1527488 (Kuwait-460)
Donor: | Kuwait Fund for Arab Economic Development (KFAED)
Total budget: | 2000000
Start date: | 2025-11-01
End date: | 2027-10-31
Project Duration: | 24 months
Target locations: | Kassala, Gedaref and Red Sea States
Implementing Partners: | TBC
Last update to tracker:
Project Locations
Red Sea | Tokar
Sinkat
Kassala | Girba
Kassala
Gedaref | Mafaza
El Rahad

## NKuwait_STRIDES_Tracker
Output | Output Indicator | Baseline | Target | Activity | STRIDES Activity Target | Kuwait-460 Target | Actual | Gedaref |  | Red Sea |  | Kassala
[8 empty] | SORR-Target | SORR-Actual_Sep | ADA-Target | ADA-Actual_Sep | MDO-Target | MDO-Actual_Sep
Output 1: Income generation, employment and food production support provided to IDPs, refugees and host community members; | 1.2 % of smallholder farmers reporting increase in agricultural production per hectare. | TBC | At least 80% | Activity 1.1: Distribute agricultural (seeds, fertilizers, and tools) and Fisheries inputs (Fishing gear, boats and engines and fish processing storage and preservation equipment) to 15,000 IDPs and Vulnerable host community households | 15000 | 4157.7388 |  | 1386 | 1000 (635 F) | 1386 |  | 1386
|  |  |  | Activity 1.2 Facilitate Access to land by 8000 IDPs, Refugees and vulnerable landless groups for agriculture activities | 8000 | 6522.6254 |  | 2174 | 1000 | 2174 |  | 2174
|  |  |  | Activity 1.3 Establish 12 Agricultural Associations and including IDPs, Refugees and host Community Members | 12 | 3.6753 |  | 1 | 0 | 1 |  | 1
| 1.1 Number of smallholder farmers receiving agriculture support, including IDPs and host communities. | 0 | 20000 | Activity 1.4 Provide agricultural extension to 20,000 households services through Farmer Field Schools in collaboration with the Ministry of Production and the Agricultural Research Stations; | 20000 | 5220.2284 |  | 1740 | 8 FFS (460 farmers) | 1740 |  | 1740
|  |  |  | Activity 1.5 Organize Two (2) Training of Trainer Workshop for 60 Fishermen on Storage, Processing and Value Addition of fish | 2 | 0 |  | 0 |  | 0 |  | 0
| 1.6 % of household stating improvement in food security based in Food Insecurity Experience Survey (FIES) | TBC | At least 80% | Activity 1.6 Initiate Seed multiplication in 6 sites with lead farmers in partnership with the Agricultural Research Stations | 6 | 2.292 |  | 1 |  | 1 |  | 1
|  |  |  | Activity 1.7: Support to livestock restocking and vaccination (mainly small ruminants) for 4,500 most vulnerable households | 4500 | 1667.4386 |  | 556 | 40 HH (80 goats) | 556 |  | 556
| 1.3 Number of groups, associations and Microenterprises receiving microgrants and savings support to establish small businesses. | 14 | 32 | Activity 1.8: Provide micro-grants to vulnerable groups and associations to 505 associations/groups and micro-enterprises to undertake small business and Incomegeneration venture. | 32 | 2.346 |  | 1 |  | 1 |  | 1
| 1.4 Number of people benefiting from emergency employment opportunities | 0 | 3000 | Activity 1.9: Support emergency employment initiatives for 3000 youth through Cash for Work initiatives. | 3000 | 1623.6075 |  | 547 |  | 547 |  | 547
| 1.5 % increase in household income attributed to project intervention. | TBC | At least 85% | Activity 1.10: Facilitate linkages with at least 2 private sector and other value chains stakeholders to promote access to market | 2 | 0.36166 |  | 0 |  | 0 |  | 0
Output 2: Renewable energy and water infrastructure/equipment provided that benefit IDPs, Refugees and host communities. | 2.1 Number and type of water resources rehabilitated, up and running | 4 | 12 | Activity 2.1: Establish/rehabilitate, upgrade and solarize 12 water resources (water awards, boreholes etc.) | 12 | 4.8567 |  | 2 |  | 2 |  | 2
| 2.2 Number of households with accessing water within 500 meter from households. | 20000 | At least 160000 people of which 60% female | Activity 2.2 Establish and train 12 CMCs on Water Resource Management, cost recovery and Sustainability to implement Cost Recovery mechanisms | 12 | 7.6616 |  | 3 |  | 3 |  | 3
| 2.3 Number of Solar Pumps distributed. | 15 | 20 | Activity 2.3 Provision of 20 Solar Water Pumps and Accessories for irrigation including gardening. | 20 | 8.9812 |  | 3 |  | 3 |  | 3
| 2.4 Number and type of farm machinery to support agricultural production. | 0 | 15 | Activity 2.4: Provide 10 agricultural machinery including Tractors and accessories to Associations to increase production. | 10 | 4.6893 |  | 2 |  | 2 |  | 2
| 2.5 % increase in area under production per household thanks to access to machinery | TBC | 85% | Activity 2.5: Distribute Household Solar Box (Torchlight, radio, charging system) to 8000 IDPs and vulnerable host households | 8000 | 2964.3447 |  | 988 |  | 988 |  | 988
| 2.6 % of households reporting reduction in GBV incidents thanks to the project. | TBC | 90% | Activity 2.7: Provide 100 Solar Street lights and Flood Lights in Gathering areas to reduce protection risks for women | 100 | 28.1842 |  | 9 |  | 9 |  | 9
Output 3: Communitybased institutions and structures in place and functioning. | 3.1 Number of CMCs established. | 15 | 12 | Activity 3.1: Establish 12 community management committees (CMCs) each with 25 members and 2-3 Sub-committees (with representation women and youth). | 12 | 4.8988 |  | 2 | 5 | 2 |  | 2
| 3.2 % of females and Youth in the CMCs | TBC | At least 40% | Activity 3.2: Conduct training for 300 CMCs on communication and advocacy skills, negotiation and mediation skills, Gender equality, SGBV and leadership skills. | 300 | 140.68 |  | 47 | 125 CMC members | 47 |  | 47
| 3.3 Number of community peace dialogue forums conducted. | 0 | 12 | Activity 3.3: Conduct 12 community peace dialogue forums | 12 | 6.5502 |  | 2 |  | 2 |  | 2
| 3.4 % of IDPs and host community members stating improvement in relations among different groups. | TBC | At least 75% | Activity 3.4 Support CMCs to organize peace events such sports, cultural and dance events emphasizing peace, social cohesion, and Co-existence among different groups. | Not specified in project docs | 0 |  | 0 |  | 0 |  | 0
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: In SORR LVGA, written target 1000HH

## Weekly Update
Week Duration | Activity Update
22nd Febto 26th Feb | New Kuwait Fund 460 – Gash Scheme (Kassala): • Joint field visit conducted with UNDP, MoPER, Gash Irrigation Department. • Most irrigation canals are buried under sand and currently non-functional; the Gash River has also experienced breaches and course changes. • For the preparation of BOQs requires a comprehensive technical study, including topographic surveys (coordinates and elevation levels), to accurately define scope and costs and thus survey engineer needs to be contracted.

## Activity Breakdown_wSDC
| Indicative Activities | Budget by Source
Outputs | Indicative Activities | Kuwait (USD) | SDC (USD) | Total (USD) | Total Target | Kuwait_TargetContribution
Output 1: Income generation, employment and food production support provided to IDPs, refugees and host community members | Activity 1.1: Distribute agricultural (seeds, fertilizers, and tools) and Fisheries inputs (Fishing gear, boats and engines and fish processing storage and preservation equipment) to 15,000 IDPs and Vulnerable host community households; | 152000 | 396375 | 548375 | 15000 | 4157.7388
| Activity 1.2 Facilitate Access to land for 8,000 IDPs, Refugees and vulnerable landless groups for agriculture activities | 30000 | 6795 | 36795 | 8000 | 6522.6254
| Activity 1.3 Establish 12 Agricultural Associations and including IDPs, Refugees and host Community Members | 10000 | 22650 | 32650 | 12 | 3.6753
| Activity 1.4 Provide agricultural extension to 20,000 households services through Farmer Field Schools in collaboration with the Ministry of Production and the Agricultural Research Stations | 20000 | 56625 | 76625 | 20000 | 5220.2284
| Activity 1.5 Organize Two (2) Training of Trainer Workshop for 60 Fishermen on Storage, Processing and Value Addition of fish | 0 | 11905 | 11905 | 2 | 0
| Activity 1.6 Initiate Seed multiplication in 6 sites with lead farmers in partnership with the Agricultural Research Stations | 35000 | 56625 | 91625 | 6 | 2.292
| Activity 1.7: Support to livestock restocking and vaccination (mainly small ruminants) for 4,500 most vulnerable households | 100000 | 169875 | 269875 | 4500 | 1667.4386
| Activity 1.8: Provide micro-grants to vulnerable groups and associations to 505 associations/groups and micro-enterprises to undertake small business and Income-generation ventures | 50000 | 632013 | 682013 | 32 | 2.346
| Activity 1.9: Support emergency employment initiatives for 3000 youth through Cash for Work initiatives. | 401444 | 340319 | 741763 | 3000 | 1623.6075
| Activity 1.10: Facilitate linkages with at least 2 private sector and other value chains stakeholders to promote access to market | 10000 | 45300 | 55300 | 2 | 0.36166
| Sub-total- Output 1 | 808444 | 1738482 | 2546926
Output 2: Renewable energy and water infrastructure/equipment provided that benefit IDPs, Refugees and host communities. | Activity 2.1: Establish/rehabilitate, upgrade and solarize 12 water resources (water awards, boreholes etc.) | 230999 | 339751 | 570750 | 12 | 4.8567
| Activity 2.2 Establish and train 12 CMCs on Water Resource Management, cost recovery and Sustainability to implement Cost Recovery mechanisms | 20000 | 11325 | 31325 | 12 | 7.6616
| Activity 2.3 Provision of 20 Solar Water Pumps and Accessories for irrigation including gardening. | 120000 | 147225 | 267225 | 20 | 8.9812
| Activity 2.4: Provide 10 agricultural machinery including Tractors and accessories to Associations to increase production. | 200000 | 226501 | 426501 | 10 | 4.6893
| Activity 2.5: Distribute Household Solar Box (Torchlight, radio, charging system) to 8000 IDPs and vulnerable host households | 66667 | 113250 | 179917 | 8000 | 2964.3447
| Activity 2.7: Provide 100 Solar Street lights and Flood Lights in Gathering areas to reduce protection risks for women | 26667 | 67950 | 94617 | 100 | 28.1842
| Sub-total- Output 2 | 671000 | 906002 | 1570335
Output 3: Community-based institutions and structures in place and functioning. | Activity 3.1: Establish 12 community management committees (CMCs) each with 25 members and 2-3 Sub-committees (with representation women and youth). | 20000 | 28992 | 48992 | 12 | 4.8988
| Activity 3.2: Conduct training for 300 CMCs on communication and advocacy skills, negotiation and mediation skills, Gender equality, SGBV and leadership skills. | 10000 | 11325 | 21325 | 300 | 140.68
| Activity 3.3: Conduct 12 community peace dialogue forums | 20000 | 16640 | 36640 | 12 | 6.5502
| Activity 3.4 Support CMCs to organize peace events such sports, cultural and dance events emphasizing peace, social cohesion, and Co-existence among different groups. | 16000 | 16640 | 32640 |  | 0
| Sub-total- Output 3 | 66000 | 73597 | 139597
Total Direct Costs | Outputs 1-3 + Project Management+ Risk Modifier | 1900000 | 3912993 | 5812993
Indirect Costs | UN Coordination Levy (1%) | 0 | 42260 | 42260
| General Management Services Cost (8%) | 0 | 313039 | 313039
| General Management Services Cost (5%) | 100000 | 0 | 100000
| Sub-total Indirect Costs | 100000 | 355299 | 455299
Grand Total |  | 2000000 | 4268292 | 6867916
1545444
354556
1904761.9048
1796945.1932
|  | 107816.7116 | DPC
|  | 246739.2884 | Managment cost
Note on E14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Amna Tameem did a slight correction on this column

## Activity Budget 2026 Kuwait
| Indicative Activities | Budget by Source |  |  |  | Target
Outputs | Indicative Activities | Total Budget Kuwait (USD) | AWP 2026 Budget | Budget /2027 | Budget per state 2026 | Total STRIDS Project Target | Kuwait Target Contribution | Target Per state
Output 1: Income generation, employment and food production support provided to IDPs, refugees and host community members | Activity 1.1: Distribute agricultural (seeds, fertilizers, and tools) and Fisheries inputs (Fishing gear, boats and engines and fish processing storage and preservation equipment) to 15,000 IDPs and Vulnerable host community households; | 152000 | 102000 | 50000 | 34000 | 15000 | 4158 | 1386
| Activity 1.2 Facilitate Access to land for 8,000 IDPs, Refugees and vulnerable landless groups for agriculture activities | 30000 | 30000 | 0 | 10000 | 8000 | 6523 | 2174.3333
| Activity 1.3 Establish 12 Agricultural Associations and including IDPs, Refugees and host Community Members | 10000 | 10000 | 0 | 3333.3333 | 12 | 4 | 1.3333
| Activity 1.4 Provide agricultural extension to 20,000 households services through Farmer Field Schools in collaboration with the Ministry of Production and the Agricultural Research Stations | 20000 | 20000 | 0 | 6666.6667 | 20000 | 5220 | 1740
| Activity 1.5 Organize Two (2) Training of Trainer Workshop for 60 Fishermen on Storage, Processing and Value Addition of fish | 0 | 0 | 0 | 0 | 2 | 0 | 0
| Activity 1.6 Initiate Seed multiplication in 6 sites with lead farmers in partnership with the Agricultural Research Stations | 35000 | 35000 | 0 | 11666.6667 | 6 | 2 | 0.66667
| Activity 1.7: Support to livestock restocking and vaccination (mainly small ruminants) for 4,500 most vulnerable households | 100000 | 50000 | 50000 | 16666.6667 | 4500 | 1667 | 555.6667
| Activity 1.8: Provide micro-grants to vulnerable groups and associations to 505 associations/groups and micro-enterprises to undertake small business and Income-generation ventures | 50000 | 50000 | 0 | 16666.6667 | 32 | 2 | 0.66667
| Activity 1.9: Support emergency employment initiatives for 3000 youth through Cash for Work initiatives. | 301444 | 101444 | 200000 | 33814.6667 | 3000 | 1642 | 547.3333
| Activity 1.10: Facilitate linkages with at least 2 private sector and other value chains stakeholders to promote access to market | 10000 | 0 | 10000 | 0 | 2 | 0 | 0
| Sub-total- Output 1 | 708444 | 398444 | 310000 | 132814.6667
Output 2: Renewable energy and water infrastructure/equipment provided that benefit IDPs, Refugees and host communities. | Activity 2.1: Establish/rehabilitate, upgrade and solarize 12 water resources (water awards, boreholes etc.) | 230999 | 201190.4 | 29808.6 | Procurement | 12 | 5 | 1.6667
| Activity 2.2 Establish and train 12 CMCs on Water Resource Management, cost recovery and Sustainability to implement Cost Recovery mechanisms | 20000 | 20000 | 0 |  | 12 | 8 | 2.6667
| Activity 2.3 Provision of 20 Solar Water Pumps and Accessories for irrigation including gardening. | 120000 | 53092 | 66908 |  | 20 | 9 | 3
| Activity 2.4: Provide 10 agricultural machinery including Tractors and accessories to Associations to increase production. | 200000 | 75000 | 125000 |  | 10 | 5 | 1.6667
| Activity 2.5: Distribute Household Solar Box (Torchlight, radio, charging system) to 8000 IDPs and vulnerable host households | 66667 | 66667 | 0 |  | 8000 | 2964 | 988
| Activity 2.7: Provide 100 Solar Street lights and Flood Lights in Gathering areas to reduce protection risks for women | 26667 | 26667 | 0 |  | 100 | 28 | 9.3333
| Sub-total- Output 2 | 671000 | 442616.4 | 221716.6 |  |  |  | 0
Output 3: Community-based institutions and structures in place and functioning. | Activity 3.1: Establish 12 community management committees (CMCs) each with 25 members and 2-3 Sub-committees (with representation women and youth). | 20000 | 20000 | 0 | 6666.6667 | 12 | 5 | 1.6667
| Activity 3.2: Conduct training for 300 CMCs on communication and advocacy skills, negotiation and mediation skills, Gender equality, SGBV and leadership skills. | 10000 | 10000 | 0 | 3333.3333 | 300 | 141 | 47
| Activity 3.3: Conduct 12 community peace dialogue forums | 20000 | 20000 | 0 | 6666.6667 | 12 | 7 | 2.3333
| Activity 3.4 Support CMCs to organize peace events such sports, cultural and dance events emphasizing peace, social cohesion, and Co-existence among different groups. | 16000 | 16000 | 0 | 5333.3333 |  | 0 | 0
| Sub-total- Output 3 | 66000 | 66000 | 0 | 22000
Total Direct Costs | Outputs 1-3 + Project Management+ Risk Modifier | 1900000
Indirect Costs | UN Coordination Levy (1%) | 0
| General Management Services Cost (8%) | 0
| General Management Services Cost (5%) | 100000
| Sub-total Indirect Costs | 100000
Grand Total | Activity Budget | 2000000 | 907060.4

## Procurement -Item distribution
1 | Solar streetlights
2
Area | Locality | State | Quantity
Aroma Town | Aroma locality | Kassala | 10
New Halfa Town | New Halfa Town | Kassala | 10
Khashm Elgirba | Khashm Elgirba | Kassala | 10
3 | Solar lanterns
# | Destination Name | Locality Name | State Name | Solar Lanterns | Status
1 | Elmafaza town | Elmafaza | Gedaref | 670 |  | Status | Ongoing
2 | Gedaref Town | Gedaref | Gedaref | 670 |  |  | Procured - Completed works
3 | Elhawata | Elrahad | Gedaref | 660 |  |  | Planned
8 | Aroma Town | Aroma locality | Kassala | 660
9 | New Halfa Town | New Halfa Town | Kassala | 670
10 | Khashm Elgirba | Khashm Elgirba | Kassala | 670
Total |  |  |  | 3200
4 | Water irrigation pumps—Locations:
# | Destination Name | Locality Name | State Name | Irrigation pumps | Status
1 | Kassala Town | Kassala | Kassala | 3
2 | Bandigeaw | West Galabat | Gedaref | 1
3 | Arbaat | Elganob Eloleeb | Red Sea | 6
5 | Water projects-- Locations
# | Destination Name | Locality Name | State Name | Irrigation pumps | Status
1 | New Halfa | New Halfa | Kassala | 3
2 | Khorelaban | Khashm Elgirba | Kassala | 1
3 | Sinkat | Sinkat | Red Sea | 1
4 | Jabait | Sinkat | Red Sea | 1
5 | Sankat | Sinkat | Red Sea | 1
Note on F11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ahmed Adam @Amna Tameem please complete this column as we'll soon be preparing a report for Kuwait-460
Note on F23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ahmed Adam @Amna Tameem please complete this column as we'll soon be preparing a report for Kuwait-460
Note on F31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Ahmed Adam @Amna Tameem please complete this column as we'll soon be preparing a report for Kuwait-460