## Project_FactSheet
Project Name: | Supporting Durable Solutions in Sudan: Multi-Year Capacity to Operationalise Solutions
Donor: | Swiss Agency for Development & Cooperation (SDC) + UNHCR
Total budget: | CHF 1,523,000
Start date: | 2025-01-01
End date: | 2027-12-31
Project Duration: | 36 months
Target locations:
Implementing Partners:
Last update to tracker:

## SDC(DS)_Tracker
Outcome | Outcome Indicator | Outcome_Baseline | Outcome_Target | Output | Output Indicator | Output_Baseline | Output_Target | Activities | Comment ¦ 2025 | Progress comment ¦ Aug 2026 | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | Status
[11 empty] | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Outcome 1: Policies and principles of durable solutions are utilized by relevant humanitarian, development, peacebuilding, and Government actors/ de facto authorities and mainstreamed into both national and state-level strategies and operational programming | # of state-level strategies and operational programs that explicitly reference and incorporate durable solutions policies and principals | 0 | 4 | Output 1.1: State-level solutions strategies developed by local government. | # of state-level strategies developed | 0 | 4 | 1.1.1 Establish Durable Solutions Unit in RCO | Onboarding the Knowledge Management Specialist and the Durable Solutions Associate marked a milestone in building DSU's institutional capacity | N/A | 2026 Q2: TRUE; 2026 Q3: FALSE | Done
| % of solutions actors who have received training on durable solutions principals | 0 | 50% |  |  |  |  | 1.1.2 Bi-annual missions to Sudan by Professor Kaelin, with mission reports | Engagement of expert scheduled for 2026 emphasizes commitment to technical excellence and durable solutions. | First mission was completed in May 2026 and the next one is planned for Sept 2026 | 2026 Q2: FALSE; 2026 Q4: FALSE; 2027 Q2: FALSE; 2027 Q4: FALSE | 2026
| # of projects or initiatives implemented at national and statelevel that are aligned to durable solutions principals | 0 | 10 | Output 1.2: Key documents for humanitarian and development work in Sudan have durable solutions mainstreamed and key durable solutions indicators are integrated. | Durable solutions marker has been integrated into # of key documents including HRP, UNDAF, agencies annual planning documents and relevant INGO programmes | 1 | 1 | 1.2.1 Through state-level DSWGs develop state-level durable solutions strategies | Key Durable Solutions indicators related to employment and livelihoods, as well as the protection of housing, land, and property (HLP) rights, were successfully integrated into the 2025 MSNA, enhancing the assessment’s ability to capture solutions-related needs and gap.as wel in inerim Cooperation Framwork and HNRP | The Action Plans for Al Jazirah and Gadaref are currently under development, while those for Blue Nile, Kassala, and White Nile are under revision. Khartoum is not applicable. | 2026 Q2: FALSE | Action plans*
[8 empty] | 1.2.2 Integration of durable solutions into HRP, CERF criteria of support, UNDAF, ICSP, and NGOS/INGOs guidelines, and other government localised plans and frameworks in Sudan | Drafting of IDP Returns Guidance Note reflects strategic commitment to policy alignment and guidance by 2025. | Work on the HNRP 2026 is yet to start. The CERF criteria of support, UNDAF, and ICPS are not applicable. Guidelines for NGOs/INGOs and Government Plans are planned. | 2026 Q4: FALSE | Done
Outcome 2: Enhanced Solutions Coordination Structures - Inclusive durable solutions coordination structures at national and state levels are functional and effective. | # of state-level DSWG’s are established and functional. | 4 | 5 | Output 2.1: National and statelevel DSWGs have developed and implemented an action plan to promote durable solutions. | DSWG action plans for promoting durable solutions is developed and implemented. | 0 | 4 | 2.1.1 Re-establish state-level DSWGs. | Blue Nile, Gadaref, Kassala, White Nile ADSWG reestablished in 2026 | Aj Jazirah ADSWG was established in May 2026 | 2026 Q2: FALSE; 2026 Q3: FALSE; 2027 Q1: FALSE; 2027 Q2: FALSE | Done
| # of state-level DSWG’s with government leadership | 0 | 4 | Output 2.2: State-DSWG are established and functional in all targeted states. | # of DSWGs meetings conducted | 2 | 8 | 2.2.1 Develop state-level DSWG action plans | 1. Bi weekly National DSWG Co Chairs Meetings Conducted: Held consistently from January to December 2025, ensuring continuous national level coordination and decision-making. 2. Monthly National DSWG Meetings Convened: Organized regularly from January to July 2025, facilitating structured engagement of national stakeholders. 3. State Level ADSWG Meetings Operationalized:  Regular monthly meetings conducted in White Nile, Kassala, Blue Nile, and Gadaref.  Blue Nile and Gedaref ADSWGs established/ reactivated/, strengthening state level mechanisms.  Locality level DSWG structures initiated with meetings held in Nertiti, Golo, and Um Dogukan (Central Darfur) as part of the establishment process. | 1. Bi weekly National DSWG Co Chairs Meetings Conducted: Held consistently from January to August 2026, ensuring continuous national level coordination and decision-making. 2. Monthly National DSWG Meetings Convened: Yet to start. 3. State Level ADSWG Meetings Operationalized:  Ad-hoc meetings conducted in Al Jazirah, White Nile, Kassala, Blue Nile, and Gadaref. | 2026 Q2: FALSE | Done
| # of state-level durable solutions strategies developed | 0 | 2 | Output 2.3: INGOs has been integrated into state-level DSWG’s. | # of joint missions conducted | 1 | 5 | 2.3.1 Conduct durable solutions capacity building and development initiatives at federal and state-level | A joint mission by UNHCR, UNDP, and DRC was successfully conducted to support the establishment of Durable Solutions Working Groups (DSWGs) in Kassala and Blue Nile. The mission engaged in bilateral meetings with key government line ministries—including Finance, Agriculture, and Social Affairs—as well as UN agencies, international and national NGOs, and private sector stakeholders, strengthening coordination and ensuring broad institutional buy‑in | Several capacity-building missions were held in the five states. Aj Jazirah in May Blue Nile, White Nile, Kassala and Gadaref in July. More session will be planned for November to manage knowledge management hubs for ADSWG. | 2026 Q2: FALSE | Done- KS
[5 empty] | # of DSWGs integrating INGOs and NNGos in its structure | 2 | 6 |  | Integration of Plan International, ADRA, and DRC as co-chairs enhanced coordination at multiple levels. | INGO and NGO is intigrated in Aj Jazirah ADSWG. | 2026 Q2: FALSE
Outcome 3: Joint area-based solutions-focused programmes are identified, implemented, and scaled up at the locality/state level. | # of joint area-based solutions initiatives and programmes developed in consultation with beneficiaries and coordinated with state Governments. | 0 | 3 | Output 3.1: Locality-level durable solutions analysis iscompleted in selected localities. | # of locality-level durable solutions analysis completed | 0 | 3 | 3.1.1 Conduct locality-level durable solutions analysis in selected states. | Locality-level Durable Solutions analyses were conducted in Golo, Nertiti, and Um Dukhun under the leadership of the Locality DSWG co-chaird by DRC. | Locality-level durable solutions analysis has been completed in Gadaref and Kassala, while the analysis is planned for Al Jazirah and Blue Nile. It has not yet been planned for White Nile. | 2026 Q2: FALSE; 2026 Q3: FALSE | Only BN
| Number and quality of joint solutions related initiatives and programmes developed, implemented or strengthened. | 0 | 3 |  |  |  |  | 3.1.2 Based on outcomes of durable solutions analysis develop state/locality level action plans | A Solutions Response Plan was developed to address the needs of returnees in Blue Nile arriving from South Sudan, based on the joint mission findings of UNHCR, UNDP, and DSU conducted from 4–11 September 2025, which also supported the establishment of the ADSWG in Blue Nile. | Based on the outcomes of the durable solutions analysis, state- and locality-level action plans have been completed in Gadaref and Kassala. Action plans for Al Jazirah and Blue Nile are planned, while planning for White Nile has not yet started. | 2026 Q4: FALSE; 2027 Q1: FALSE | Done
| Number of solutions projects that are developed as part of their strategies, receive funds and commence implementation. | 0 | 1 | Output 3.2: Locality-level durable solutions action plans are jointly developed and implemented. | # of action plans developed jointly | 0 | 3 | 3.2.1 Support joint implementation of locality action plans | State-level ADSWG Action Plans have been developed in Blue Nile, White Nile, and Kassala to strengthen engagement and coordination at the state level. | Joint implementaion planning is under progress. | 2026 Q4: FALSE; 2027 Q1: FALSE
| Number of feedback/monitoring/ reporting mechanisms established to increase exchange of information on solutions between the displacement affected communities and DSWGs at locality level. | 0 | 1
Outcome 4: Improved durable solutions specific data collection and joint evidence base is used to inform joint durable solutions planning and programming. | Effective data management system is in-place for durable solutions which informs planning and implementation of durable solutions programmes. | 0 | 1 | Output 4.1: Agreed-upon core list of durable solutions indicators to monitor progress towards durable solutions is developed. | List of quantitative and qualitative indicators. | 0 | 1 | 4.1.1 Develop list of durable solutions indicators customised for Sudanese context. | Durable Solutions questions were included in MSNA 2025 to support informed, data-driven humanitarian planning. | The initial list of indicators was developed by DSU for 2026. DSU is collaborating with JIPS to develop a DS tracking framework and updated set of indicators. This should be done by November 2025. | 2026 Q3: FALSE; 2026 Q4: FALSE | Done
| # of joint data collection initiatives to track collaborative efforts of solutions actor including assessments, surveys and research projects. | 0 | 1 | Output 4.2: User-friendly platform is established where durable solutions can be accessed to monitor progress by durable solutions actors including integration with the national government system at the Central Bureau of Statistics and agency-run platforms including DTM. | Platform established functional, integrating various sources of data. | 0 | 1 | 4.2.1 Establish, operate and coordinate data and information platform for durable solutions. |  | Knowledge Management hub is being developed for the DSWG and the five ADSWGs. Should be done by mid October. | 2026 Q1: FALSE; 2026 Q2: FALSE; 2026 Q3: FALSE; 2026 Q4: FALSE; 2027 Q1: FALSE | Not done
| Utilization of data in planning and programming which measures the extent to which collected data is used in joint planning and programming. | 0 | 1 | Output 4.3: Capacity of durable solutions actors is strengthened to ensure collective utilization of durable solutions frameworks | # of capacity building events | 0 | 4 | 4.3.1 Capacity building, mentorship provided to CBS, VRRC, and other relevant government institutions and development partners | A two-day Durable Solutions Capacity Building Workshop was successfully conducted in Kassala State on 22–23 December 2025, bringing together 33 participants from government institutions, UN agencies, NGOs, and development partners, with 27% female representation. The workshop strengthened the capacity of state and national institutions to plan and implement Durable Solutions initiatives, contributing directly to improved coordination and technical understanding within the Area Solutions Working Group (ASWG) | Capacity building will be held to manage the KM hubs for ADSWG in November 2026. | [12 empty] | Done in Kassala

## Annual Workplan
|  |  |  | 2025 | [47 empty] | 2026 | [47 empty] | 2027
No. | AWP ¦ SIRI | Activity | Status for 2026 | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1.1.1 |  | Establish Durable Solutions Unit in RCO | Completed | bar: April 1 to December 4
1.1.1.1 |  | Durable Solution Advisor (P4) | Completed | bar: April 1 to December 4
1.1.1.2 |  | Durable Solutions Knowledge Management Coordinator | Completed | bar: January 4 to December 4
1.1.1.3 |  | Project Associate | Completed | bar: May 1 to December 4
1.1.1.4 |  | INGO Coordinator (DRC) | Completed | bar: May 4 to December 4
1.1.2 |  | Bi-annual missions to Sudan by Professor Kaelin, with mission reports
1.1.2.1 |  | 2026 Vist 1 | Completed | bar: April 1 to December 4
1.1.2.2 |  | 2026 Vist 2 | Planned | bar: September 1 to December 4
1.1.2.3 |  | 2027 Visit 1 | 2027
1.1.2.4 |  | 2027 Visit 2 | 2027
1.2.1 |  | Through state-level DSWGs develop state-level durable solutions Action Plan
1.2.1.1 |  | Al Jazirah | Under development
1.2.1.2 |  | Blue Nile | Under Revision | bar: October 1 to December 4; August 1 to August 4
1.2.1.3 |  | Gadaref | Under development | bar: July 3 to August 2
1.2.1.4 |  | Kasala | Under Revision | bar: July 2 to December 4; July 3 to August 2
1.2.1.5 |  | White Nile | Under Revision | bar: July 2 to December 4; July 3 to August 2
1.2.1.6 |  | Khartoum | Not Applicable | bar: August 1 to August 4
1.2.2 |  | Integration of durable solutions into HRP, CERF criteria of support, UNDAF, ICSP, and NGOS/INGOs guidelines, and other government localised plans and frameworks in Sudan
1.2.2.1 |  | HNRP 2025 - Link to HNRP on development | Completed | bar: December 4
1.2.2.2 |  | HNRP 2026 | Yet to start
1.2.2.3 |  | HNRP 2027 | 2027
1.2.2.4 |  | CERF criteria of support | Not Applicable
1.2.2.5 |  | UNDAF | Not Applicable
1.2.2.6 |  | ICPS | Not Applicable
1.2.2.7 |  | NGOS/INGOS guideline | Planned | bar: September 1 to October 4
1.2.2.8 |  | Government Plans | Planned | bar: September 1 to October 4
2.1.1 |  | Re-establish state-level ADSWGs.
2.1.1.1 |  | Al Jazirah | Completed | bar: May 3
2.1.1.2 |  | Blue Nile | Completed | bar: September 2
2.1.1.3 |  | Gadaref | Completed | bar: January 1
2.1.1.4 |  | Kasala | Completed | bar: January 1
2.1.1.5 |  | White Nile | Completed | bar: January 1
2.1.1.6 |  | Khartoum | Not Applicable
2.3.2 |  | Conduct durable solutions capacity building and development initiatives at federal and state-level | On hold
3.1.1 |  | Conduct locality-level durable solutions analysis in selected states.
3.1.1.1 |  | Al Jazirah | Planned | bar: August 2
3.1.1.2 |  | Blue Nile | Planned | bar: August 2
3.1.1.3 |  | Gadaref | Completed | bar: July 3 to July 4
3.1.1.4 |  | Kasala | Completed | bar: July 3 to July 4
3.1.1.5 |  | White Nile | Not Planned yet
3.1.1.6 |  | Khartoum | Not Applicable
3.1.2 |  | Based on outcomes of durable solutions analysis develop state/locality level action plans
3.1.2.1 |  | Al Jazirah | Planned | bar: August 2
3.1.2.2 |  | Blue Nile | Planned | bar: August 2
3.1.2.3 |  | Gadaref | Completed | bar: July 3 to July 4
3.1.2.4 |  | Kasala | Completed | bar: July 3 to July 4
3.1.2.5 |  | White Nile | Not Planned yet
3.1.2.6 |  | Khartoum | Not Applicable
3.2.1 |  | Support joint implementation of locality action plans | bar: September 1 to December 4
3.2.1.1 |  | Al Jazirah | Not Planned yet | bar: September 1 to December 4
3.2.1.2 |  | Blue Nile | Not Planned yet | bar: September 1 to December 4
3.2.1.3 |  | Gadaref | Not Planned yet | bar: September 1 to December 4
3.2.1.4 |  | Kasala | Not Planned yet | bar: September 1 to December 4
3.2.1.5 |  | White Nile | Not Planned yet | bar: September 1 to December 4
3.2.1.6 |  | Khartoum | Not Applicable | bar: September 1 to December 4
4.1.1 |  | Develop list of durable solutions indicators customised for Sudanese context. | Under Development
4.1.1.1 |  | Develop an initial list of durable solutions indicators to track DS in 2026 | Completed | bar: July 1
4.1.1.2 |  | Bring JIPS as a partner to develop DS framework and DS indicators | Completed | bar: July 1
4.1.1.3 |  | Develop a framework to track DS indicators in Sudan | On going
4.1.1.4 |  | Finalise 2026 DS indicators | On going
4.2.1 |  | Establish, operate and coordinate data and information platform for durable solutions. | Planned
4.2.1.1 |  | Develop a DSWG Knowledge Management hub for DSWG Members | Completed
4.2.1.2 |  | Develop an ADSWG knowledge management hub for Al Jazirah | Planned
4.2.1.3 |  | Develop an ADSWG knowledge management hub for Blue Nile | Planned
4.2.1.4 |  | Develop an ADSWG knowledge management hub for Gadaref | Planned
4.2.1.5 |  | Develop an ADSWG knowledge management hub for Kassala | Planned
4.2.1.6 |  | Develop an ADSWG knowledge management hub for White Nile | Planned
4.2.1.7 |  | Develop an ADSWG knowledge management hub for Khartoum | Not Applicable
4.2.1.8 |  | Establish a common database to support DS indicators | Planned
4.3.1 |  | Capacity building, mentorship provided to CBS, VRRC, and other relevant government institutions and development partners | Planned | bar: December 4
4.3.1.1 |  | Train ADSWG to manage KM hub in Al Jazirah | Planned
4.3.1.2 |  | Train ADSWG to manage KM hub in Blue Nile | Planned
4.3.1.3 |  | Train ADSWG to manage KM hub in Gadaref | Planned
4.3.1.4 |  | Train ADSWG to manage KM hub in Kasala | Planned
4.3.1.5 |  | Train ADSWG to manage KM hub in White Nile | Planned
4.3.1.6 |  | Train ADSWG to manage KM hub in Khartoum | Not Applicable
5 |  | Small Scale Investment
5.1 |  | 2025
5.1.1 |  | Project 1- Bule Nile ¦ Upgrading three hand pumps to mini water yard | On going | bar: December 2 to February 4
5.1.2 |  | Project 2 - Bule Nile ¦ Rehblitation of two health Center | Completed | bar: December 2 to February 4
5.1.3 |  | Project 3- Bule Nile¦ Cash for work | Completed
5.1.4 |  | Project 4- Kassala ¦ A Capacity Building Workshop under the Kassala Area Solutions Working Group (ASWG) was held from 22–23 December 2025 with 30 participants, 27% of whom were women. | Completed | bar: December 3 to December 4
5.2 | 4.1.7 | 2026
5.2.1 |  | Project 1 | Not Planned
5.3 |  | 2027
5.3.1 |  | Project 1 | Not Planned
6 |  | Crisis modifier
6.1 |  | 2025 | None
6.1.1 |  | Project 1
6.2 | 4.1.8 | 2026
6.2.1 |  | Project 1 | Not Planned
6.3 |  | 2027
6.3.1 |  | Project 1 | Not Planned
Note on D42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: On hold as RC does not want to do a federl level workshop yet.

## WeeklyUpdates
Week Duration | Update
8th Feb to 12th Feb | SDC Durable Solutions - Kassala: • Government has implemented its 12 February ultimatum for IDPs at Alk Karama2 IDPs site to vacate the site amidst chaos and vandalization of humanitarian assets; • IDPs from Darfur and Khordofans are being relocated to Al Karama 1. Rest of IDPs are either to return or locally integrate. • The AHCT engaged extensively with state authorities to advocate for voluntary return of the IDPs.
15th Feb to 19th Feb | 1. UNDP Kassala team took part in the advocacy meeting on the eviction of IDPs from Al Karama site with the State Government 2. UNDP Kassala team attended the Moment of Reflection Workshop organized by UNHCR where we delivered a presentation on Enhancing Humanitarian-Development-Peace Nexus – Opportunities for Collaboration, Coordination and Synergies.
22nd Feb to 26th Feb

## Beneficiaries_Reached
R&R Pillar: Number of People Targeted and Reached in 2026 (as of Sept)
[5 empty] | Direct: Targets 2026 |  |  | Direct: Actual as of Sept |  |  | In direct: Targets 2026 |  |  | Indirect: Actual Sept |  |  | Total direct+indirect
Pillar Name | Project Name | Intervention | State | Location | Direct Ben Female | Direct Ben Male | Total Direct | Actual Female | Actual Male | Actual F+M | Indirect Ben Female | Indirect Ben Male | Total indirect | Actual Female | Actual Male | Actual F+M
R&R Pillar: Number of People Targeted and Reached in 2026 (as of Sept) | SIRI - Supporting Durable Solutions in Sudan: Multi-Year Capacity to Operationalise Solutions | Capacity building/vocational training/training | Kassala | Kassala
| SIRI - Supporting Durable Solutions in Sudan: Multi-Year Capacity to Operationalise Solutions | Improve Access to Health Services | Blue Nile | Bau
| SIRI - Supporting Durable Solutions in Sudan: Multi-Year Capacity to Operationalise Solutions | Productive/Critical Infrastructure | Blue Nile | Bau
| SIRI - Supporting Durable Solutions in Sudan: Multi-Year Capacity to Operationalise Solutions | Water/Yard Rehabilitation & Solarization | Blue Nile | Bau
| SIRI - Supporting Durable Solutions in Sudan: Multi-Year Capacity to Operationalise Solutions | Cash for work | Blue Nile | Bau